## DB Apps (hidden)
| Business Unit | Total no. of Apps | Apps in Scope with ITO | Apps not in scope with ITO
| GM | 342 | 82 | 260
| CTO | 290 | 107 | 183
| CT | 78 | 24 | 54
| AM | 39 | 13 | 26
| CIB | 69 | 18 | 51
|  | 818 | 244 | 574
| Business Unit | WIN 2003 to 2012 | WIN 2008 to 2012 | Solaris to Linux 7.x | RedHat Ent 4, 5.2 to Linux 7.x | IBM AIX to to Linux 7.x | SLES 11 SP2 and below to SLES 11 SPx | Solaris Sparc 10 to to Linux 7.x | Solaris X64 to to Linux 7.x (64 bit) | Oracle Sloaris Sparc 10 and below to | IBM Z/OS 2.2 and below to ?? | Vendor OS to ?? | NetApp to ?? | VMWare ESXI 5.5 and below to latest VMWare
| GM | 4 | 87 |  |  | 5 | 86 | 53 | 34 | 4 |  | 8 | 1 | 1
| CTO | 9 | 117 |  | 4 | 8 | 29 | 45 | 17 | 11 |  | 25 | 4 | 7
| CT |  | 25 |  |  | 4 | 7 | 11 |  | 5 | 3 | 5
| AM | 1 | 20 |  |  | 1 | 7 | 7 | 1 | 3
| CIB | 5 | 38 |  |  | 2 | 10 | 20 |  | 1 | 2
|  | 19 | 287 | 0 | 4 | 20 | 139 | 136 | 52 | 24 | 5 | 38 | 5 | 8
|  | 2.578% | 38.94% | 0% | 0.5427% | 2.714% | 18.86% | 18.45% | 7.056% | 3.256% | 0.6784% | 5.156% | 0.6784% | 1.085%
|  | 41.52% |  |  |  |  | simple | [6 empty] | 737
|  | 30% | 40% | 20% | 5% | 5%
|  | Simple | Medium | Complex | Very complex | Not Applicable/Decomission
Re-host | Image Migration | NA - By ITO
Binary Migration
Re-Install
Recompile
Source Code Mod.
Upgrade | COTS
Custom
Re-factor | Source Code Upgrade

## Instructions
Application Migration Factories Estimation Model
Important Notes: a. This excel model works in Office 365 supporting the Microsoft Excel 2016 version or later. Does not work with earlier versions of Excel b. The efforts does not cover Functional Regression tests, System tests, Integration tests,Performance tests or any other special tests. Only unit test and Smoke test hours are included. Other hours have to be estimated by Testing Services team and incorporated appropriately c. Database efforts are to be calculated through separate estimation tracks and added to the Application treatment efforts to get total efforts for the application d. More than one treatment line might be applicable for an application. In such cases, individual treatment line efforts are added to get the total efforts for the application. For example, same application may undergo an Unix to Linux transformation as well as a Java Modernization treatment
Introduction
This estimation model covers 10 factory tracks which in turn maps to 19 sub tracks. Each track/sub track scope are listed in the Factory tracks tab.. This model is at the second level of 3 levels of estimation models. The purpose of this model is to arrive at final estimates for proposal responses with a high level of confidence. The model is built based on the following components
Tab | Descriptions | Instructions
Factory Input | This is the only tab that a solution provider needs to use to input the data for complexity calculations. These are highlighted in light yellow colored cells. The data entered are: 1. Application Name 2. Select Factory Line Sub Track name from the drop down list 3. There are drop down lists for each complexity factor. Select appropriate complexity levels from these lists. 4. The sheet also has logic to calculate complexity for each complexity factor and sums up all complexity factor values thus calculated to get a total complexity for ec application. This is multiplied with the Simple complexity effort hours from the 3-Point estimation model (picked up from the Model tab corresponding to the factory treatment sub track applicable for this application) to arrive at the total effort estimate for the application 5. Steps 1 to 4 are repeated for each application | Each complexity input has a drop down with values. Please select the closest drop down value that matches your scenario for each dropdown. Where, a drop down is not applicable, the dropdown will be disabled and values can not be entered
Model | Model gives the relative wightage of each complexity parameter and also the three point estimates, which form the basis for this estimation model. a. 3-Point estimates for each sub track. This has efforts for 3 complexity levels - Simple, Medium and Complex. (The complexity assumptions for each of these 3 complexity levels are shown in the 3-Point estimation complexities tab) b. These efforts are established for each sub track based on detailed WBS for each track and actual efforts observed through multiple deliveries c. The Model tab also defines the applicable factors and their weightages for each sub track d. The total of all the complexity factors for a track totals upto 100%. Optional complexity factors such as Concurrent users and Internationalization take the total weightage beyond 100% | No access would be provided to this unless there is a very specific need to change this
3-Point Estimation Model | This tab has an extract from Level 1 estimation Model which shows the effort corresponding to Simple, Medium amd Complex for each sub track.The complexities corresponding to Simple, Medium and Complex are defined in the 3-Point estimation model sheet. The 3-point estimation efforts are used as benchmarks as these numbers are validated through multiple deliveries through factories for specific complexity levels | This sheet is just for information purposes only
Lookup | Look up tables in the Lookup tab list the various levels of complexities for each Complexity factor and grades the complexity factors in a scale of 1 to 10. There is one Lookup table for each Complexity factor. Each Lookup table has the following: a. Complexity Factor name b. Defined complexity levels for the factor with range of values that correspond to each complexity level c. The complexity levels could range from 1 to a maximum of 10 with 1 being the least complexity and 10 representing the maximum complexity. d. Not all factors will have 10 levels. Some factors may have less than 10 levels as well e. The complexity level that corresponds to Min value of the 3-Point estimation model will be level 1 f. The complexity that corresponds to Max value of the 3-Point estimation model will be the level number shown at row 2 in the sheet against each table g. IT should be noted that there could be complexity levels beyond the Max value complexity level. This provides the ability for the model to extrapolate efforts beyond the maximum value of the 3 point model h. Each Complexity Lookup table also has an item called "Not Avl or Medium Complexity" . If data is not available for a complexity factor, the default complexity assumed would be Medium | No access will be provided to this tab unless there is a very specific need to change this
Complexity and Effort Calculation Logic (Factory Input Tab) | For each application that is entered in the Input tab, the following steps are performed to arrive at total effort. 1. For the sub track selected, applicable complexities and their weightages are obtained from the Model tab 2. For each complexity factor, based on Complexity level for the factor selected in the Factory Input tab,Complexity level for Max estimate obtained from Lookup tab and Complex to Simple Ratio and Weight for the factor obtained from the Model tab, complexities are calculated based on the following formula: (Complexity Level for a factor /Complexity level for Max estimate)*Complex to Simple Ratio*Weight for the factor 3. Complexity thus calculated are summed up for all complexity factors to arrive at the Cumulative Complexity Factor 6. This Cumulative Complexity Factor is multiplied with the estimated hours corresponding to the complexity level "Simple" in the 3 point estimates. 7. This way, the estimates are arrived through an interpolation between simple and complex points of the 3 point estimation model and also extrapolated beyond the Complex estimates to take care of the Extra Complex scenarios
Phase Wise Migration Estimates | The Migration estimates applies the life cycle model splits and totals up the estimates and arrives at a mile stone schedule as well | This will be generated but will have a flexibility to change certain parameters
Staffing Model | Provides overall staffing allocations - locations (onshore-offshore), resource-wise split, indicative price calculations and rampup models | Update indicative % split for Onshore-Offshore resource Update indicative % split for resource tiers (mention 0% if any particular role not required for particular track / complexity) Update cost rate and price rates for each role The Cost and Price are generated

## Treatment Line Scope
Treatment Line Scope and assumptions
The following table provides the scope of activities, inputs for each factory treatment line and inherent assumptions that go with
Note: Any application not conforming to below criteria need to be assessed on case-by-case basis and migration track, approach and estimates arrived at accordingly
Factory Treatment Line/Sub track | Treatment Line Scope and specific Assumptions | Complexity Factor Limits
Windows Upgrade | Scope includes migrating custom applications running on legacy Windows server Operating systems starting from Windows 2003 and above to latest Windows 2012 or above and deploying them on Public or Private Clouds or virtual or physical enterprise data centers. Like for like migrations with minimum code or configuration changes with No changes to UI, languages or framework components
| Upgrading to latest .Net framework is outside the scope of this treatment track | Migrate custom Windows applications from Windows 2003 and later to Windows 2012 or 2016. Versions prior to Windows are to be estimated and priced separately.
| Third party components if any must be compatible with target environment with No change to their usage characteristics | Source code size not greater than 0.5M LoC or 300 application components (screens, reports, batch programs, User controls added together)
| Includes any interface changes that are minor and any minor changes to data access code at the application layer due to database version upgrades | No. of interfaces limited to 35
| Includes unit testing and smoke testing efforts and does not include any other testing efforts | Max no of DB tables limited to 300
| Migration does not involve changes to interfaces such as API / System call / RPC (Remote Procedure call) in the code. the existing code that consumes these interfaces is assumed to work in target environment too with No code changes | Max. no. of migration environments limited to
No incompatible memory issues such as 16 bit/32 bit source to 64 bit targets
database and data Migration efforts are not included. these are estimated through a separate track
No Performance Tuning or Performance improvements. No degradation of existing Performance
Linux to Linux | Migrating custom applications from legacy Linux Operating systems to latest Linux Operating system versions on Public or Private Clouds or virtual or physical enterprise data centers. Applicable source system versions of Linux starting from RHEL 4 or above and SLES 8 or abov or Ubuntu 14 or above. Target would be the latest RHEL 7 or above or SLES 11 or above
| Like for like migrations with minimum code or configuration changes with no changes to UI or framework components | Source code size not greater than 0.5M LoC or 300 application components (screens, reports, batch programs, User controls added together)
| Languages supported by this treatment line include Java, C++, Perl, Scripts | Max no of DB tables limited to 300
| Third party components if any must be compatible with target environment with no change to their usage characteristics and will continue to be consumed the same way as before | No. of interfaces limited to 35
Includes any interface changes that are minor and any minor changes to data access code at the application layer due to database version upgrades
Includes unit testing and smoke testing efforts and does not include any other testing efforts
Migration does not involve changes to interfaces such as API / System call / RPC (Remote Procedure Call) in the code. The existing code that consumes these interfaces is assumed to work in target environment too with no code changes
No incompatible memory issues such as 16 bit/32 bit source to 64 bit targets
Database and data migration efforts are not included. These are estimated through a separate track
No Performance Tuning or Performance improvements. No degradation of existing performance
U2L-Java | Scope includes migrating Java applications from UNIX to LINUX and making any changes to the code required to enable the application to work on the target LINUX environment. Scope also includes deploying on Public or Private Clouds or virtual or physical enterprise data centers. Typical examples of such code changes include replacing UNIX calls with related LINUX calls, changing any complier options, runtime directives etc that are different in LINUX as compared to UNIX, changing hard code IP addresses, file paths etc.
No upgrades to Java or JEE versions or any framework components like spring, hibernate, struts etc
No architecture changes. Only Lift and shift with changes to code / configuration will be done to suit the target environment
Third party components if any must be compatible with target environment with no change to their usage characteristics and will continue to be consumed the same way as before
Includes unit testing and smoke testing efforts and does not include any other testing efforts
Database and data migration efforts are not included. These are estimated through a separate track
If an application has both Java and non-Java code, those code components will be estimated separately through 2 different tracks
No Performance Tuning or Performance improvements. No degradation of existing performance
U2L-Others | Scope includes migrating Non-Java (C, C++, Perl) applications running on legacy UNIX OS such as Solaris, AIX or UP-UX to Linux distributions such as RHEL 7 or above, SLES 11 or above etc. Non Java application migration from UNIX to LINUX is more complex due to deeper OS or platform bindings. Scope also includes deploying to Public or Private Clouds or virtual or physical enterprise data centers.
| Linmited to migrating C,C++, Perl and scripts. Efforts for any other language need to be estimated separately | Source UNIX versions include Solaris 8 or above or AIX 5 or above or HP UX 11i V1 or above.
| No upgrades to frameworks or third party libraries | Source code size not greater than 0.5M LoC or 300 application components (screens, reports, batch programs, User controls added together)
| No incompatible Memory dependent source code such as endianness issues or 16/32 bit issues | No. of interfaces limited to 35
| No architecture changes | No. of third party components limited to 30
| Third party components if any must be compatible with target environment with no change to their usage characteristics and will continue to be consumed the same way as before | Max no of DB tables limited to 300
No Performance Tuning or Performance improvements. No degradation of existing performance
Includes unit testing and smoke testing efforts and does not include any other testing efforts.
Database and data migration efforts are not included. These are estimated through a separate track
If an application has both Java and non-Java code, those code components will be estimated separately through 2 different tracks
ASP to .Net | Upgrade custom applications running on Classic ASP to to ASP.Net web pages. This treatment track does not cover any other treatments such as upgrading VB components. Scope also includes deploying to Public or Private Clouds or virtual or physical enterprise data centers.
| No architecture or functional changes | Source code size not greater than 0.5M LoC or 300 application components (screens, reports, batch programs, User controls added together)No. of interfaces limited to 35
| No changes to user interface | No. of third party components limited to 30
| All 3rd party components and Activex controls are compatible in the target environment. | Max no of DB tables limited to 300
No VB or Activex component will be converted to .Net. If such components exist, they will be addressed through the VB to .Net track and the effort will be added
Includes unit testing and smoke testing efforts and does not include any other testing efforts
All database/data migration efforts are not included and will be through a separate track
VB to .Net | VB code will be updated to latest .Net specifications and data access components will be upgraded to latest ADO.Net specifications. IF this is a thick client application, then the VB UI pages will be migrated to VB.Net UI.Scope also includes deploying to Public or Private Clouds or virtual or physical enterprise data centers.
No functional changes
| All 3rd party components and Activex controls are compatible in the target environment. If upgraded licenses are needed, the client will be responsible to provide these licenses. If no equivalent versions are available and if they need to be custom developed, such efforts are not included | Source code size not greater than 0.5M LoC or 220 application components (screens, reports, batch programs, User controls added together)No. of interfaces limited to 35
| Any ASP code will not be migrated to ASP.Net. This will be addressed by a separate track and efforts will be separately calculated if this is required. | No. of third party components limited to 30
| No changes to UI. If the VB UI needs to be converted to ASP.Net, this will be done through a separate track and will not be part of this effort | Max no of DB tables limited to 300
All database/data migration efforts are not included and will be through a separate track
No Performance Tuning or Performance improvements. No degradation of existing Performance
Includes unit testing and smoke testing efforts and does not include any other testing efforts
VB.Net to ASP.Net | VB.Net UI will be converted to ASP.Net Web UI. All the third party UI components are replaced by suitable browser based components. Scope also includes deploying to Public or Private Clouds or virtual or physical enterprise data centers.
| The resultant ASP.Net UI will be functionally equivalent but may not maintain the VB.Net UI look and feel | Source code size not greater than 0.7M LoC or 220 application components (screens, reports, batch programs, User controls added together)
| It is assumed that all VB.Net UI controls are supported through equivalent ASP.Net UI controls | No. of third party components limited to 30
| All third party Activex controls will be mapped to equivalent ASP.Net controls and such controls should beprovided by the customer. If upgraded licenses are needed, the client will be responsible to provide these licenses. If no equivalent versions are available and if they need to be custom developed, such efforts are not included in this estimate and need to be estimated separately and priced | No. of interfaces limited to 35
| All user defined controls will be converted to equivalent ASCX controls. Source code must be available for user controls | Max no of DB tables limited to 300
No Performance Tuning or Performance improvements. No degradation of existing performance
All database/data migration efforts are not included and will be through a separate track
Includes unit testing and smoke testing efforts and does not include any other testing efforts
CFML to ASP .Net | Cold Fusion HTML pages will be converted to ASP.Net web page, Cold fusion code will be converted to VB.Net code and cold fusion data access components will be converted to ADO.Net components. Scope also includes deploying to Public or Private Clouds or virtual or physical enterprise data centers.
| It is assumed that all Cold Fusion UI controls are supported through equivalent ASP.Net UI controls | Source code size not greater than 0.7M LoC or 220 application components (screens, reports, batch programs, User controls added together)
| If Adobe controls such as Flash or any other such third party controls that are OS dependent are used, they may need additional efforts to handle and have not been factored in the efforts | No. of third party components limited to 30
| No Performance Tuning or Performance improvements. No degradation of existing performance | No. of interfaces limited to 35
| All database/data migration efforts are not included and will be through a separate track | Max no of DB tables limited to 300
Includes unit testing and smoke testing efforts and does not include any other testing efforts
All third party Activex controls will be mapped to equivalent ASP.Net controls and such controls should beprovided by the customer
MS Access to .Net | Access UI will be generated as MVC ASP.Net forms or ASP.Net web forms based on business and technical needs. Access event code and VBA code will become VB.Net code components consumed through the MVC controller classes. MS Access unbound forms and VBA code will be converted to VB.Net through the VB to .Net tool. All data access code will be coverted to ADO.Net framework automatically. MS Access data and schema will be migrated to SQL Server or any other RDBMS. Scope also includes deploying to Public or Private Clouds or virtual or physical enterprise data centers.
| The ASP.Net UI generated will be functionally equivalent to the Access UI but will not have the same look and f+B74:C80eel as Access forms. If same look and feel needs to be preserved, this will be additional UI work that will not be covered by the estimation model | Source code size not greater than 0.7M LoC or 220 application components (screens, reports, batch programs, User controls and VBA code added together)
| It is assumed that all VB.Net UI controls are supported through equivalent ASP.Net UI controls | No. of third party components limited to 30
| All third party Activex controls will be mapped to equivalent ASP.Net controls and such controls should beprovided by the customer | No. of interfaces limited to 35
| All user defined controls will be converted to equivalent ASCX controls. Source code must be available for user controls | Max no of DB tables limited to 300
No Performance Tuning or Performance improvements. No degradation of existing performance
All database/data migration efforts are not included and will be through a separate track
Includes unit testing and smoke testing efforts and does not include any other testing efforts
Lotus Notes to O365 | Lotus Notes applications are converted to SharePoint/O365 applications.Lotus Notes databases migrated to SQL Server databases. User interface/forms are generated through SharePoint/O365 templates. Workflows are taken care by SharePoint/O365 workflow capabilities.
| No changes to be done on documents / attachments being migrated | Maximum size of database limited to 100GB
| Administrator restricted file types may not be moved to Office 365 through the tool (.EXE, MP3 etc. if restricted by Client administrators). Such documents will need to be migrated manually and will need additional efforts which will need be estimated separately | Max no. of application objects limited to 100
| User creation / provisioning in O365 is not included as part of the transformation/migration effort | Max no of workflows limited to 2 per application.
All content in rich text boxes will be aligned as per the O365 templates. Additional effort would be needed if any customization is needed
The look and feel of the target applications will not be the same as in Louts Notes due to platform restrictions.
Workflows will be of simple approval flows that can go upto 6 levels of approvals. Anything other that will need to be estimated separately
Decommission | This track enables decommissioning applications, archiving databases, manage access to archived data and decommissioning the applications based on dependencies. Prior to decommissioning, if any interfaces to other applications need to be addressed, that is also included in the scope of these estimates
| Any UI or report program that need to be developed to retrieve archived data will be additional and not included in the estimates. | Max No. of interfaces limited to 35
| Testing efforts are limited to smoke testing. System and integration test efforts are not included. Performance tests are also not included in the estimates | Max no of tables limited to 300
Efforts include only decommissioning of the applications.Efforts to decommission underlying infrastructure is not included
Archival database software should have been pre-installed and available.
Scope includes archiving relational data only. Archiving of non-relational databases and file systems are not covered in this estimation model
COTS application Migration | COTS application migration refers to migrating COTS applications to target operating systems on cloud/virtualized or physical Data centre infrastructure. The COTS products in scope will include those that have no customization capabilities. The COTS products in scope will exclude all COTS products that are enterprise solutions or have extensive customization features and complex architecture such as SAP, Oracle e-Biz solution, Microsoft Dynamics, SaaS products, Business Intelligence products, Content management products, B2B Comerce solutions, Industry focused solutions such as Cerner, Guidewire etc. There are exclusive practice teams who will be involved in the migration of such products and migration efforts widely vary depending on the extent of customization and other business process and technical integration needs. So such products are not in the scope of this estimation model
Migration does not involve any type of changes in the COTS application components
COTS vendor will carryout the migration of application components, and deploy the application in each environment - testing, UAT, production etc.
DXC will only manage the implementation, and also if needed will carryout System Integration
COTS migration does not involve any functionality changes, the functionality will be migrated like-for-like
COTS vendor will also perform the manual remediation, including interface connectivity parameters hardcoded in application code. No other type of code changes will be done.
In case the COTS application is not compatible with the target environment (even after version upgrades), COTS vendor will recommend a suitable replacement. DXC will provide inputs if requested.
In case COTS vendor recommends a replacement, client will evaluate the replacement and provide necessary approvals to COTS vendor. DXC will provide inputs if requested.
DXC or COTS vendor will not prepare data for any type of test. Client will provide the test data of production standards (including unit / smoke test)
Client will ensure the COTS vendor takes the ownership of migrating the COTS application. If DXC is required to migrate such applications, the approach need to be revisited and re-estimated
It is the COTS vendors' responsibility to ensure performance of the migrated system on the target environment.
Client will coordinate with the stake holders of migration implementation, like internal application owners, outsourcing partners, and ensure their timely participation and contribution
DB Upgrade- MySQL/SQL Server | The upgrades include only relational to relational databases. Scope involves upgrading from older to latest database versions and migrating database schema and data This does not include installation of database software but includes migrating database schemas, data, configuration of database parameters to suit the target database. SQL Server 2000 and above and MySQL V3.0 and above are in scope for this upgrade. The databaseschema will be migrated to a fresh target database system. In place upgrades are not considered. Sanity checks are performed on the migrated database but does not involve extensive tests. Scope of work includes porting data to the target RDBMS and accommodate any data type changes and configuration accordingly
DB Upgrade - Oracle | The upgrades include only relational to relational databases. Scope involves upgrading from older to latest database versions and migrating database schema and data This does not include installation of database software but includes migrating database schemas, data, configuration of database parameters to suit the target database . Oracle legacy versions from 5.x and above are in scope for this upgrade. Sanity checks are performed on the migrated database but does not involve extensive tests. Scope of work includes porting data to the target RDBMS and accommodate any data type changes and configuration accordingly
Cross DB Migration - Non Cluster | Cross DB migration implies migrating from one relational database to another. The source and target databases should comply with the SQL standards. This migration involves migrating database schema and data from a non-clustered source database to a non-clustered target environment. The databaseschema will be migrated to a fresh target database system. In place upgrades are not considered. Sanity checks are performed on the migrated database but does not involve extensive tests. Scope of work includes any refactoring of stored procedures, triggers etc as well as porting data to the target RDBMS and accommodate any data type changes and configuration accordingly
Cross DB Migratio - Clustered | Cross DB migration implies migrating from one relational database to another. The source and target databases should comply with the SQL standards. This migration involves migrating from a non-clustered or clustered source database to a clustered target environment. The databaseschema will be migrated to a fresh target database system. In place upgrades are not considered. Sanity checks are performed on the migrated database but does not involve extensive tests. Scope of work includes any refactoring of stored procedures, triggers etc as well as porting data to the target RDBMS and accommodate any data type changes and configuration accordingly
Refactor Java - Java/MW upgrade | Scope of this treatment track is limited to upgrading the custom Java application to the latest Java/JEE specification and upgrade middleware to the latetst specification and migrate/deploy to target environment (Public, Private clouds or enterprise data centers)
Like for like migration and changes to application functionaliy have not been included
No changes to UI considered.
No changes to framework components other than any middleware or JEE/Java specification related changes
Includes efforts for unit tests and smoke tests. Does not include effort for other system/ integration tests. UAT support efforts included. Efforts for fixing defects due to various tests included. Efforts for Performance or security tests not included
Includes efforts for special deployment configurations such as clustering/load balancing but does not include efforts for configuring the related infrastructure.
Scope does not include any performance tuning or architecture changes
Refactor Java - Spring, Hibernate | Scope for this treatment includes refactoring to move into Spring and Hibernate frameworks. In the process, will also upgrade the Java/JEE versions to latest specification level and migrate to target Cloud/Enterprise Data Center servers. The scope involves migrating into or upgrading to latest framework versions of Spring and Hibernate. Any heavy weight components such as EJB are replaced with light weight Spring Components. All JDBC implementation are replaced with Hibernate framework
Like for like migration and changes to application functionaliy have not been included
No changes to UI considered.
Includes efforts for unit tests and smoke tests. Does not include effort for other system/ integration tests. UAT support efforts included. Efforts for fixing defects due to various tests included. Efforts for Performance or security tests not included
Includes efforts for special deployment configurations such as clustering/load balancing but does not include efforts for configuring the related infrastructure.
Scope does not include any performance tuning or architecture changes
Refactor Java -AppserverMigration | The scope for this treatment involves migrating from one Java Application Server to another and deploying the application to the new Java App Server target on Public/Private cloud or enterprise data centers
Like for like migration and changes to application functionaliy have not been included
No changes to UI considered.
No changes to framework components other than any middleware or JEE/Java specification related changes
Includes efforts for unit tests and smoke tests. Does not include effort for other system/ integration tests. UAT support efforts included. Efforts for fixing defects due to various tests included. Efforts for Performance or security tests not included
Includes efforts for special deployment configurations such as clustering/load balancing but does not include efforts for configuring the related infrastructure.
Scope does not include any performance tuning or architecture changes

## Complexity Definitions
Complexity | Definition | Upper Limits
Source to TargetOS | Complexity due to migration from Source to target Operating Systems. The extent of jump between the source and target OS determines the complexity. For example, Unix to Linux would be more complex than a Linux to Linux migration. | Source OS systems include only Windows, Linux and UNIX systems. All mainframe and other legacy OS are excluded. The oldest OS version for Windows will be Windows 2003. For Linux, it is RH3 or SLES 8. For UNIX, it will be AIX 5.x, HP-UX 11i V1 or Solaris 7
Business Rule/UIComplexity | This factor indicates complexity of business functionality, rules or complex business process workflows, Complex user interfaces etc | Limited to max 2 workflows per application. UI Complexity involves having to provide rich user interfaces that are not by default supported by the target frameworks and complexity in terms of no. and complexity of UI components in each screen are high
Source to Target Framework | Upgrades to framework such as .Net and JEE from earlier to latest versions. The larger the difference between source and target frameworks, greater will be the complexity | Oldest .Net framework version in scope will be .Net 2.0. Oldest version of JEE framework will be JEE 1.2. For MS Access databases, theearliest version supported would be MS Access 2000.
Source to target DB | Complexity due to migration from source to target datanbases. The extent of jump between the source and target databases determines the complexity. For example, migrating from one RDBMS to another such as Oracle to MySQL will be more complex than a version upgrade of the same database. For application treatment tracks, this factor represents the impact of such database changes on the application. | Source databases would be relational databases. Non relational databases and file system migrations are not included in these estimates. The estimation model currently provides for database upgrades of Oracle version 5.x and above, , SQL Server 2000 and above and MySQL V3 and above. For other databases, cross Database migration estimates are in scope. No restrictions on source and target databases as long as they are both relational databases conforming to SQL standards
App Size Complexity (SLOC, Screens, reports) | This defines the size complexity in terms of LoC or no. of application components (screens, reports, batch programs). If both LoC and application components are given, the greater of the two will be taken for complexity calculations | Max LoC limited to 800K and 220 application objects(screen/report/programs/Scripts). For Lotus Notes to O365 migration, the max number of application objects are limited to 100
DB Size/No. of DB Objects | This takes into account the size complexity in terms of number of DB objects such as tables, stored procedures, triggers etc. The larger the number, greater is the complexity | Max no. of DB objects limited to 300
Data Size | This takes into account the complexity due to data volume. The larger the DB size, greater is the complexity | Max data size covered by this model is 2TB. For Lotus Notes to O365, the max data size is limited to 100GB due to migration tool limitations. Beyond this, the data migrations have to be executed in multiple chunks and hence efforts will need to be calculated separately
No. of 3rd Party Components | This measures the complexity due to handling third party components during migration. This might require code changes if there is a change in the interfaces to these components. The number of such references to third party components in the code determines the complexity | Max. No of interfaces limited to 30
No. of Environments | This denotes the number of environments such as Production, QA, Dev, UAT, SIT, Performance test, DR etc that needs to be supported while deploying the treated applications. The higher the number of environments, greater is the complexity | Max no of environments limited to 8
No. of External Interfaces | This denotes the complexity due to handling impact to external interfaces during migration (external to the organization and could include eco system or business partners. The greater the number of interfaces, greater is the complexity. At this point, we may not know the underlying protocol for these interfaces. The interfaces could be file interfaces, FTP, web interfaces, Web Services, API based interfaces etc | Max. no of external interfaces limited to 35
No. of internal Interfaces | This denotes the complexity due to handling impact to internal interfaces during migration. The greater the number of interfaces, greater is the complexity. At this point, we may not know the underlying protocol for these interfaces. The interfaces could be file interfaces, FTP, Web Services, API based interfaces, COM inerfaces, Java interfaces etc | Max no. of internal interfaces limited to 35
Architecture Complexity | This denotes the complexity due to architecture tiers, distributed architecture due to clustering, load balancing,failoveretc. Greater the number of tiers or nodes, greater the complexity | Unclustered, Clustered and large enterprise H/A are the threee architecture configurations available
Concurrent users | This is the complexity due to requirement of serving concurrent users and the need to handle the performance, scalability and load fall outs due to that. The greater the number of concurrent users, greater is the complexity. Any adverse impact to these aspects need to be handled. This is an optional factor and over and above the weightage for regular factors | Max concurrent user limit provided for is 2000. Upto 50 concurrent users, this factor will have no weightage and will have no impact on the feffort.
Location | When applications are to be migrated across multiple source and target data centers across multiple countries and with multiple languages introduces complexities and communication overheads that need to be handled. This is an optional factor and over and above the weightage for regular factors | Has 3 levels, Single location, Multi-location and Multi-location,Multi-language. Single location would mean there will be no weightage and no impact on the effort
Internationalization/Localization | When applications need to handle multiple languages (Single Byte or Double Byte or Multi Byte) and whether the internationalization and localization requirements are limited to UI layer or across all layers including databases imposes additional complexities that need to be handled. This is an optional factor and over and above the weightage for regular factors | This has levels Single Language, Multi-language Single byte,Multi-language Multi-yte and further Based on whether only UI or UI and database need to be handled. If Single language, then this complexity has no weightage and will not have any impact on the effort
Doc /Data Availability | Extent of document and data availability such as test plans, test cases, test data, deployment scripts and documents, architecture documents, release notes etc determine the complexity of this factor. | It is assumed that by default, 70% of such document/data are available. If the availability is less than 70%, then additional complexity will be calculated. If the availability is greater than 70%, then the complexity is accordingly reduced

## 3-Point Estimates (hidden)
Treatment ↓ / Complexity Factor → | Simple (person hours) | Medium (person hours) | High (person hours)
Windows to Windows Migration | 490 | 900 | 1480
Unix to Linux (U2L) - Java | 180 | 240 | 1140
Unix to Linux (U2L) - Other Technologies | 610 | 730 | 1060
Binary Application Migration |  | 240
Packaged Application Migration | 60 |  | 1200
Note: Any parameters beyond the range given below need to be assessed on case-by-case basis and estimated
Contains all activities, including project management
Treatment ↓ / Complexity Factor (effort in person hours) → | Simple | Medium | Complex
Windows to Windows Migration
Windows Platform Upgrade | 200 | 250 | 300
Source 'OS / Platform: | Windows 20012 | Windows 2008 | Windows 2003
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Environments: | 1 | 2,3 | 4,5
Servers: | 1 - Single tiered | 2,3 - Multi-tiered | 4-6 - Multi-tiered with Load balancing and failover
Database tables/Objects | <100 | 100-199 | 200-350
ASP to ASP.NET | 600 | 1200 | 1600
Source 'OS / Platform: | Windows 2012 | Windows 2008 | Windows 2003
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Third Party Components/References | <5 | 5-10 | 11-20
Environments: | 1 | 2,3 | 4,5
Servers: | 1 - Single tiered | 2,3 - Multi-tiered | 4-6 - Multi-tiered with Load balancing and failover
Database tables/Objects | <100 | 100-199 | 200-350
VB.Net to ASP.Net | 795 | 1740 | 2574
Source 'OS / Platform: | Windows 20012 | Windows 2008 | Windows 2003
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Third Party Components/References | <5 | 5-10 | 11-20
Environments: | 1 | 2,3 | 4,5
Servers: | 1 - Single tiered | 2,3 - Multi-tiered | 4-6 - Multi-tiered with Load balancing and failover
Database tables/Objects | <100 | 100-199 | 200-350
MS-Access to ASP.NET | 684 | 1518 | 2389
Source 'OS / Platform: | Windows 2012 | Windows 2008 | Windows 2003
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Third Party Components/References | <5 | 5-10 | 11-20
Environments: | 1 | 2,3 | 4,5
Servers: | 1 - Single tiered | 2,3 - Multi-tiered | 4-6 - Multi-tiered with Load balancing and failover
Database tables/Objects | <100 | 100-199 | 200-350
Upgrade .Net Framework | 847 | 1855 | 2743
Source OS / Platform: | Windows 2012 | Windows 2008 | Windows 2003
.Net Framework version | .Net 3.5 and above | .Net 3.0 and above | .Net 2.0 and above
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Third Party Components/References | <5 | 5-10 | 11-20
Environments: | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
VB to VB.NET or C#.Net | 1000 | 3600 | 6000
OS / Platform: | Windows 2008/2012 | Windows 2003 | Windows 2000
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Third Party Components/References | <5 | 5-10 | 11-20
Environments: | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
CFML to ASP. NET | 887 | 1518 | 2165
OS / Platform: | Windows 2008/2012 | Windows 2003 | Windows 2000
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Third Party Components/References | <5 | 5-10 | 11-20
Environments: | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
Unix to Linux U2L Migration
Linux Platform Upgrade | 200 | 250 | 300
Source OS / Platform: | Same version on source and target | Source Linux versions include RHEL 5 or above or SLES 9 or above. | Source Linux versions include RHEL 4 or above and Ubuntu 14 or above or SLES 8 or above.
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Environments: | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
U2L - Java | 330 | #REF! | #REF!
OS / Platform: | RHEL Linux 5.x,6.x | RHEL Linux 4.x | Unix / Solaris
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Environments: | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
U2L - C, C++, Perl | #REF! | #REF! | #REF!
OS / Platform: | RHEL Linux 5.x,6.x | RHEL Linux 4.x | Unix / Solaris
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Environments: | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
Java Refactor - Java /JEE Version Upgrade
Java /JEE Version | Java EE6, EE7 | Java EE5, J2EE1.4 | J2EE1.3, J2EE1.2
Number of Objects (Screens / Forms / Reports / Programs): | <25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Environments: | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
Third Party Components/References | <5 | 5-10 | 11-20
Java Refactor - Refactor to Spring and Hibernate
Java/JEE Version | Java EE6, EE7 | Java EE5, J2EE1.4 | J2EE1.3, J2EE1.2
Source Framework | Spring, Hibernate lower versions | Struts, DAO | No MVC framework used
Number of Objects (Screens / Forms / Reports / Programs) | <25 | 26-90 | 91-150
Interfaces | 1 | 2,3 | 4,5
Third Party Components/References | <5 | 5-10 | 11-20
Environments | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
Java Refactor - App Server Migration
Java/JEE Version | Java EE6, EE7 | Java EE5, J2EE1.4 | J2EE1.3, J2EE1.2
Number of Objects (Screens / Forms / Reports / Programs) | <25 | 26-90 | 91-150
Interfaces | 1 | 2,3 | 4,5
Third Party Components/References | <5 | 5-10 | 11-20
Environments | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
Lotus Notes Migration
Lotus Notes to Sharepoint O365 | 130 | 265 | 519
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Data Size: | <10 GB | 11-30 GB | 31-50 GB
COTS Migration
COTS Upgrade (migrating to new environment with vendor support) | 100 | 125 | 175
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Environments | 1 | 2,3 | 4,5
Servers: | <10 GB | 11-30 GB | 31-50 GB
Decommission
Decommission | 207 | 348 | 519
Interfaces: | <2 | 3-5 | 6-10
Environments: | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
Database Migration
DB - MySQL/MS SQL/Postgres/DB2 Upgrade | 115 | 145 | 178
Clustering / # of Nodes: | Standalone Server | Clustered - 2 Nodes | Clustered - 3/4 Nodes
Number of DB Objects: | <100 | 101-300 | 301-500
DB size: | <500 GB | 500 GB - 1 TB | 1 TB - 1.5 TB
DB - Oracle Upgrade | 144 | 233 | 296
Clustering / # of Nodes: | Standalone Server | Clustered - 2 Nodes | Clustered - 3/4 Nodes
Number of DB Objects: | <100 | 101-300 | 301-500
DB size: | <500 GB | 500 GB - 1 TB | 1 TB - 1.5 TB
DB - Vendor Change, Non Cluster | 618 | 1572 | 2471
Number of DB Objects: | <100 | 101-300 | 301-500
DB size: | <500 GB | 500 GB - 1 TB | 1 TB - 1.5 TB
DB - Vendor Change, Clustered (2 Nodes assumed) | 791 | 1784 | 2766
Number of DB Objects: | <100 | 101-300 | 301-500
DB size: | <500 GB | 500 GB - 1 TB | 1 TB - 1.5 TB
Note on A1: 1st iteration base estimates

## Factory Input
Sr.No | Application Name | Migration Factory Line and Sub Track | Source to TargetOS | Business Rule/Workflow/UI | Source to Target Language/ Framework | Source to target DB | Source code Size | No. of screens/Reports/Programs | No. of DB Objects | Data Size | No. of 3rd Party Components | No. of Environments | No. of Ext Interfaces | No. of internal Interfaces | Architecture Complexity | Concurrent users | Location | Internationalization/Localization | Doc Availability | Total Complexity | Total Hours | Base Effort (Hrs) | OS Complexity | Business rule/UI Complexity | Framework Complexity | DB Complexity | Sorcecode Size Complexity | App Objects Complexity | DB Objects Complexity | Data Size Complexity | 3rd Party Components Complexity | Environment Complexity | External Interface Complexity | Internal Interface Complexity | Architecture Complexity Calculation | Concurrent User Complexity | Location Complexity | I18N and L10N Complexity | Doc Availability Complexity
1 | EAI |  |  | Complex | [8 empty] | Between 21-30 | Between 11-20 |  | Not accessed directly |  |  | It exists and is usable even if it is somewhat out of date | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
2 | Papperslöst |  |  | Moderately Complex |  |  | 15-49k | 110-129 | 121-150 tables | 750 GB-1 TB | 11 to 15 | 4 to 5 | Between 3-5 | Between 1-2 | Clustered 3 tier | between 1,001 to 2,000 | Multi-Location | UI+ Data- single-byte | It exists and is usable even if it is somewhat out of date | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
3 | Siebel |  |  | Very Complex | [8 empty] | Between 1-2 | Between 3-5 |  | between 1,001 to 2,000 |  |  | It exist but no Error Database | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
4 | SPD |  |  | Very Complex | [8 empty] | Between 21-30 | Between 11-20 |  | less than 100 |  |  | Exist in segregated form but usable | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
5 | Telenor.se |  |  | Complex | [8 empty] | Between 6-10 | Between 6-10 |  | between 1,001 to 2,000 |  |  | No documentation | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[20 empty] | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #N/A | #NAME? | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Phase-wise Effort
Phase-wise Effort Estimation
Migration Factory Line | Number of applications | Total hours | Analysis (including Source Code Analysis) | Design and Planning | Transformation Treatment (including unit testing, deployments during Dev & test) | Testing | UAT Support | Deployment / Release | Warranty Support | Project Management | Unit Total | Unit Total for target platform | Grand Total | Architect/ Migration Lead | Sr. Developers | Developer | Test Lead/Test Manager | Sr. Tester | Tester | Build & Deploy Engineer | PM | Total
Windows Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Linux to Linux | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
U2L-Java | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
U2L-Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ASP to .Net | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VB to .Net | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VB.Net to ASP.Net | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CFML to ASP .Net | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MS Access to .Net | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lotus Notes to O365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DeCommission | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COTS Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DB Upgrade- MySQL/SQL Server | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DB Upgrade - Oracle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cross DB Migration - Non Cluster | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cross DB Migratio - Clustered | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refactor Java - Java/MW upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refactor Java - Spring, Hibernate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refactor Java - Middleware Migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refactor Java - UI Modernization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refactor Java - Stateless & scalable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Microsoft | 0 | 0
[14 empty] | Java | 0 | 0
[14 empty] | U2L | 0 | 0
[14 empty] | Database | 0 | 0

## Staffing Model
Man Hours/Month
Onsite | 20% | 160
Offshore | 80% | 180
Total Duration | 36 | Months
| Onsite/Offshore | Staffing Roles/Month No | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
| Onsite | Program Manager/Project Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Architect/Transformation Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior Developers (Microsoft) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior Developers (Java) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior Developers (U2L) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior Analyst (Database) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Developers (Microsoft) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Developers (Java) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Developers (U2L) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Analyst (Database) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test Lead/Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior Testers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Testers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Build & Deploy Engineers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Offshore | Program Manager/Project Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Architect/Transformation Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior Developers (Microsoft) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior Developers (Java) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior Developers (U2L) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior Analyst (Database) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Developers (Microsoft) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Developers (Java) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Developers (U2L) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Analyst (Database) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test Lead/Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Senior Testers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Testers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Build & Deploy Engineers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Model
Migration Factory Line | Simple | Medium | Complex | Complex to Simple Ratio | Factory line Group | Source to TargetOS | Business Rule/Workflow/UIComplexity | Source to Target Framework | Source to target DB | App Size Complexity (SLOC, Screens, reports, Scripts) | DB Size/No. of DB Objects | Data Size | No. of 3rd Party Components | No. of Environments | No. of External Interfaces | No. of internal Interfaces | Architecture Complexity | Concurrent users | Location | Internationalization/Localization | Doc /Data Availability | Analysis (including Source Code Analysis) | Design and Planning | Transformation Treatment | Testing | UAT Support | Deployment / Release | Warranty Support | Project Management | Total | Architect/Migration Lead | Sr. Developers | Developer | Test Lead/Test Manager | Sr. Tester | Tester | Build & Deployment Engineer | PM | Total
Windows Upgrade | 200 | 250 | 300 | 1.5 | 1 | 30% | 0% | 0% | 0% | 30% | 5% | 0% | 5% | 10% | 5% | 5% | 5% | 15% | 5% | 15% | 5% | 10% | 10% | 35% | 10% | 5% | 20% | 0% | 10% | 100% | 11.5% | 18.25% | 33.5% | 2% | 4.25% | 6.5% | 14% | 10% | 100%
Linux to Linux | 200 | 250 | 300 | 1.5 | 2 | 30% | 0% | 0% | 0% | 30% | 5% | 0% | 5% | 10% | 5% | 5% | 5% | 15% | 5% | 15% | 5% | 10% | 10% | 35% | 10% | 5% | 20% | 0% | 10% | 100% | 11.5% | 18.25% | 33.5% | 2% | 4.25% | 6.5% | 14% | 10% | 100%
U2L-Java | 330 | 550 | 1045 | 3.1667 | 3 | 20% | 0% | 0% | 0% | 30% | 5% | 0% | 5% | 10% | 10% | 5% | 10% | 15% | 5% | 15% | 5% | 10% | 10% | 45% | 5% | 5% | 15% | 0% | 10% | 100% | 12% | 19.75% | 40% | 1.5% | 2.75% | 3.5% | 10.5% | 10% | 100%
U2L-Others | 824 | 1353 | 1958 | 2.3762 | 3 | 20% | 0% | 0% | 0% | 30% | 5% | 0% | 5% | 10% | 10% | 5% | 10% | 15% | 5% | 15% | 5% | 10% | 10% | 45% | 5% | 5% | 15% | 0% | 10% | 100% | 12% | 19.75% | 40% | 1.5% | 2.75% | 3.5% | 10.5% | 10% | 100%
ASP to .Net | 600 | 1200 | 1600 | 2.6667 | 1 | 5% | 10% | 15% | 0% | 30% | 5% | 0% | 5% | 5% | 10% | 5% | 5% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
VB to .Net | 1000 | 3600 | 6000 | 6 | 1 | 0% | 10% | 0% | 0% | 40% | 5% | 0% | 15% | 5% | 15% | 0% | 5% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
VB.Net to ASP.Net | 795 | 1740 | 2574 | 3.2377 | 1 | 0% | 10% | 15% | 0% | 30% | 5% | 0% | 10% | 5% | 10% | 5% | 5% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
CFML to ASP .Net | 887 | 1518 | 2165 | 2.4408 | 1 | 10% | 10% | 0% | 0% | 30% | 5% | 0% | 10% | 10% | 10% | 5% | 5% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
MS Access to .Net | 684 | 1518 | 2389 | 3.4927 | 0 | 0% | 10% | 15% | 0% | 25% | 15% | 5% | 5% | 5% | 7% | 3% | 5% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
Lotus Notes to O365 | 130 | 265 | 519 | 3.9923 | 8 | 0% | 20% | 0% | 0% | 45% | 0% | 30% | 0% | 0% | 0% | 0% | 0% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
DeCommission | 207 | 348 | 519 | 2.5072 | 4 | 15% | 0% | 0% | 20% | 0% | 30% | 5% | 0% | 15% | 10% | 5% | 0% | 0% | 5% | 0% | 0% | 15% | 15% | 40% | 5% | 5% | 10% | 0% | 10% | 100% | 14% | 22.25% | 38% | 2% | 3.25% | 3.5% | 7% | 10% | 100%
COTS Upgrade | 100 | 125 | 175 | 1.75 | 4 | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 20% | 10% | 15% | 0% | 5% | 0% | 5% | 20% | 15% | 20% | 5% | 5% | 20% | 0% | 15% | 100% | 15% | 21% | 26% | 2.25% | 3.25% | 3.5% | 14% | 15% | 100%
DB Upgrade- MySQL/SQL Server | 115 | 145 | 178 | 1.5478 | 5 | 5% | 0% | 0% | 15% | 0% | 30% | 15% | 0% | 10% | 7% | 3% | 10% | 15% | 5% | 15% | 5% | 10% | 15% | 35% | 5% | 5% | 20% | 0% | 10% | 100% | 12.5% | 20.5% | 34.5% | 1.75% | 3.25% | 3.5% | 14% | 10% | 100%
DB Upgrade - Oracle | 143 | 233 | 296 | 2.0699 | 5 | 5% | 0% | 0% | 15% | 0% | 30% | 15% | 0% | 10% | 7% | 3% | 10% | 15% | 5% | 15% | 5% | 10% | 15% | 35% | 5% | 5% | 20% | 0% | 10% | 100% | 12.5% | 20.5% | 34.5% | 1.75% | 3.25% | 3.5% | 14% | 10% | 100%
Cross DB Migration - Non Cluster | 618 | 1572 | 2471 | 3.9984 | 7 | 5% | 0% | 0% | 0% | 0% | 35% | 15% | 0% | 15% | 7% | 3% | 15% | 15% | 5% | 15% | 5% | 10% | 15% | 35% | 5% | 5% | 20% | 0% | 10% | 100% | 12.5% | 20.5% | 34.5% | 1.75% | 3.25% | 3.5% | 14% | 10% | 100%
Cross DB Migratio - Clustered | 791 | 1784 | 2766 | 3.4968 | 7 | 5% | 0% | 0% | 0% | 0% | 35% | 15% | 0% | 15% | 7% | 3% | 15% | 15% | 5% | 15% | 5% | 10% | 15% | 35% | 5% | 5% | 20% | 0% | 10% | 100% | 12.5% | 20.5% | 34.5% | 1.75% | 3.25% | 3.5% | 14% | 10% | 100%
Refactor Java - Java/MW upgrade | 200 | 291 | 357 | 1.785 | 6 | 0% | 10% | 15% | 0% | 30% | 5% | 0% | 5% | 5% | 10% | 5% | 10% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
Refactor Java - Spring, Hibernate | 637 | 1407 | 2177 | 3.4176 | 6 | 0% | 10% | 10% | 0% | 30% | 5% | 0% | 5% | 10% | 10% | 5% | 10% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
Refactor Java - Middleware Migration | 239 | 349 | 428 | 1.7908 | 6 | 0% | 10% | 0% | 0% | 40% | 5% | 0% | 5% | 10% | 10% | 5% | 10% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
Refactor Java - UI Modernization |  |  |  |  | 6 | 0% | 20% | 15% | 0% | 25% | 5% | 0% | 5% | 5% | 7% | 3% | 10% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
Refactor Java - Stateless & scalable |  |  |  |  | 6 | 0% | 10% | 15% | 0% | 30% | 5% | 0% | 5% | 5% | 10% | 5% | 10% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
[5 empty] | These tracks need to be validated with real implementations | [20 empty] | 25% | PM
[26 empty] | 25% | Architect
[26 empty] | 15% | Test Lead
[26 empty] | 20% | Sr.Developer
[26 empty] | 15% | Sr. Testers

## Lookup
Complexity Scale Factors |  | OS Complexity Lookup |  | Business Rule /UI Complexity/Workflows |  | Source to Target Framework |  | Source to Target Database |  | App Size Complexity Look up |  |  |  | DB Size Lookup |  | Data Size Loopkup |  | Architecture Lookup |  | Third Party Components |  | Environment Lookup |  | External Interfaces |  | Internal Interfaces |  | Concurrent Usage |  | Location Complexity |  | I18N and L10N Complexity |  | Document availability
|  | 6 |  | 2 |  | 6 |  | 4 |  | 6 |  |  |  | 6 |  | 4 |  | 3 |  | 4 |  | 2 |  | 2 |  | 2 |  | 3 |  | 2 |  | 3 |  | 4
|  | Source Target OS | Complexity Rating | Criteria | Complexity Rating/Workflows | Source to Target Framework | Complexity Rating | Source to Target Database | Complexity Rating | Source code Size | Complexity Rating | No. of App objects (Screens, Reports, Programs) | Complexity Rating | No. of DB Objects | Complexity Rating | Data suze (MB) | Complexity Rating | Architecture | Complexity Rating | No. of 3rd Party Components | Complexity Rating | No. of Env | Complexity Rating | No. of Ext Interfaces | Complexity Rating | No. of internal Interfaces | Complexity Rating | Concurrent Users | Complexity Rating | Location | Complexity Rating | I18N/L10N Requirements | Complexity Rating | Test case availability | Complexity Rating
|  | Win 2016 to Win 2016 | 0 | Simple | 0 | .Net 4.5 to .Net 4.6 | 0 | Oracle 5 to 12c | 7 | 0-14k | 0 | <25 | 0 | 0-30 tables | 0 | Upto 100 GB | 0 | Unclustered | 0 | None | 0 | Upto 1 | 0 | Upto2 | 0 | Upto2 | 0 | Upto 50 | 0 | Single location | 0 | None | 0 | 90-100% | -2
|  | Win 2012 to Win 2016 | 0 | Medium | 1 | .Net 4.0 to .Net 4.6 | 1 | Oracle 6 to 12c | 6 | 15-49k | 1 | 25-49 | 1 | 31-60 tables | 1 | 100-300 GB | 2 | Clustered 3 tier | 3 | upto 5 | 1 | 2 to 3 | 1 | 2-5 | 1 | 2-5 | 1 | 50 to 100 | 1 | Multi-location | 1 | Only UI | 1 | 70-90% | -1
|  | Win 2008 Win 2016 | 2 | Complex | 2 | .Net 3.5 to .Net 4.6 | 2 | Oracle 7 to 12c | 5 | 50-99k | 2 | 50-74 | 2 | 61-90 tables | 2 | 300-500GB | 4 | Large Enterprise H/A | 6 | 6 to 10 | 2 | 4 to 5 | 2 | 6-10 | 2 | 6-10 | 2 | 100-200 | 2 | Multi-location,Language | 2 | UI+Data - single byte | 2 | 70% available | 0
|  | Win 2008 to Win 2012 | 2 | Not Avl | 1 | .Net 3.0 to .Net 4.6 | 4 | Oracle 8 to 12c | 4 | 100 - 199k | 3 | 75-89 | 3 | 91-120 tables | 3 | 500 - 750GB | 5 | Not Avl | 0 | 11 to 15 | 3 | 6 to 7 | 3 | 11-15 | 3 | 11-15 | 3 | 200-500 | 3 | Not Avl | 0 | UI+Data-Multi-byte | 3 | 60-70% | 1
|  | Win 2003 to Win 2016 | 6 | NA | 0 | .Net 2.0 to .Net 4.6 | 6 | Oracle 9 to 12c | 3 | 200-299k | 4 | 90-109 | 4 | 121-150 tables | 4 | 750GB-1TB | 6 | NA | 0 | 16 to 20 | 4 | 7 to 8 | 4 | 16-20 | 4 | 16-20 | 4 | 500-1000 | 4 | NA | 0 | Not Avl | 0 | 40-60% | 2
|  | Win 2003 to Win 2012 | 6 |  |  | Not Avl | 2 | Oracle 10g to 12c | 2 | 300-399k | 5 | 110-129 | 5 | 151-180 tables | 5 | 1TB - 1.5TB | 8 |  |  | 21 to 25 | 5 | Not Avl | 1 | 21-25 | 5 | 21-25 | 5 | 1000-1500 | 5 |  |  | NA | 0 | 20-40% | 3
|  | Win 2000 to Win 2012 | 8 |  |  | NA | 0 | Oracle 11g to 12c | 1 | 400-499k | 6 | 130-149 | 6 | 181-210 tables | 6 | 1.5TB-2TB | 10 |  |  | 26-30 | 6 | NA | 0 | 26 to 30 | 6 | 26-30 | 6 | 1500-2000 | 6 |  |  |  |  | 0-20% | 4
|  | Win 2000 to Win 2016 | 8 |  |  | Java EE7 to JavaEE7 | 0 | Oracle 12c to 12c | 0 | 500-599K | 7 | 150-169 | 7 | 211-240 tables | 7 | Not Avl | 2 |  |  | Not Avl | 2 |  |  | 31 to 35 | 7 | 31 to 35 | 7 | 2000-2500 | 7 |  |  |  |  | Not Avl | 0
|  | Win NT 4 Win 2016 | 10 |  |  | Java EE6 to Java EE7 | 1 | SQL Server 2000 to 2016 | 7 | 600-699K | 8 | 170-189 | 8 | 241-270 tables | 8 | NA | 0 |  |  | NA | 0 |  |  | Not Avl | 1 | Not Avl | 1 | Not Avl | 0 |  |  |  |  | NA | 0
|  | Win NT 4 to Win 2012 | 10 |  |  | Java EE5 to JavaEE7 | 2 | SQL Server 2005 to 2016 | 6 | 700-799K | 9 | 190-220 | 9 | 271-300 tables | 9 | [8 empty] | NA | 0 | NA | 0 | NA | 0
|  | RH7 to RH7 | 0 |  |  | J2EE 1.4 to JavaEE7 | 4 | SQL Server 2008 to 2016 | 4 | Not Avl | 2 | Not Avl | 2 | Not Avl | 3 | Lotus Notes Data
|  | Suse11 to Suse 11 | 0 |  |  | J2EE1.3 to Java EE7 | 6 | SQL Server 2012 to 2016 | 2 | NA | 0 | NA | 0 | NA | 0 | Upto 5GB | 0
Effort from 3 Point Estimator Model |  | RH6 to RH7 | 2 |  |  | J2EE1.2 to JavaEE7 | 8 | SQL Server 2014 to 2016 | 1 |  |  | Lotus Notes |  |  |  | 5GB to 10GB | 2
Simple Effort | 200 | Suse 10 to Suse 11 | 2 |  |  | Not Avl | 2 | SQL Server 2016 to 2016 | 0 |  |  | Upto 15 | 0 |  |  | 10GB to 15GB | 4
Medium Effort | 200 | RH5 to RH 7 | 4 |  |  | NA | 0 | MySQL v 3.xMySQL v 5.7 | 7 |  |  | 16-25 | 3 |  |  | 15GB to 30GB | 6
Complex Effort | 250 | Suse 9 to Suse 11 | 4 |  |  | Access 2013 to .Net | 0 | MySQL v 4.xMySQL v 5.7 | 6 |  |  | 26-40 | 6 |  |  | 30GB to 50GB | 8
Complex/Simple Ratio | 1.25 | RH4 to RH7 | 6 |  |  | Access 2010 to .Net | 1 | MySQL v 5.0MySQL v 5.7 | 4 |  |  | 41-60 | 8 |  |  | 50GB to 70GB | 10
|  | Suse 8 to Suse 11 | 6 |  |  | Access 2007 to .Net | 2 | MySQL v 5.1MySQL v 5.7 | 3 |  |  | 61-80 | 10 |  |  | 70GB to 100GB | 12
Source to TargetOS |  | RH3 to RH7 | 8 |  |  | Access 2003 to .Net | 4 | MySQL v 5.5MySQL v 5.7 | 2 |  |  | 81-100 | 12 |  |  | Not Avl | 2
Business Rule/UIComplexity |  | AIX 7.2 to Linux | 2 |  |  | Access 2002 to .Net | 6 | MySQL v 5.6MySQL v 5.7 | 1 |  |  | Not Avl | 3 |  |  | NA | 0
Source to Target Framework |  | Solaris 11.x to Linux | 2 |  |  | Access 2000 to .Net | 8 | MySQL v 5.7MySQL v 5.7 | 0 |  |  | NA | 0
Soure to Target Middleware |  | HP UX 11i V3 to Linux | 2 |  |  | NA | 0 | Not Available | 4
Source to target DB |  | AIX 7.1 to Linux | 4 |  |  | Not Avl | 3 | NA | 0
App Size Complexity (SLOC, Screens, reports) |  | Solaris 10 to Linux | 4 |  |  |  |  | Relational to Relational w/o StoredProc | 2
DB Size/No. of DB Objects |  | AIX 6.1 to Linux | 6 |  |  |  |  | Relational to Relational with StoredProc | 4
Data Size |  | HP UX 11i V2 to Linux | 6 |  |  |  |  | Mainframe DB2 to Relational | 6
No. of 3rd Party Components |  | Solaris 9 to Linux | 6 |  |  |  |  | Mainframe DB2 and VSAM to relational | 8
No. of Environments |  | AIX 5L5.1,5.2, 5.3 to LINUX | 8 |  |  |  |  | DB 400 to Relational | 8
No. of Ext Interfaces |  | Solaris 8,7 to Linux | 8 |  |  |  |  | Mainframe IMS to Relational | 10
No. of internal Interfaces |  | HP UX 11i V1 to Linux | 8 |  |  |  |  | Not Avl | 2
Architecture Complexity |  | Not Avl or Medium Complexity | 4 |  |  |  |  | NA | 0
Concurrent users
Location |  | NA | 0
Internationalization/Localization
Doc /Data Availability
Workflow |  | Source to TargetOS | Business Rule/UIComplexity | [6 empty] | Soure to Target Middleware | Source to target DB | DB Size/No. of DB Objects | Data Size | No. of Environments | No. of Ext Interfaces |  |  | Architecture Complexity | Concurrent users | Internationalization/Localization | Doc /Data Availability

## Deliverables
Deliverables
i. Baselined Project Plan and Schedule
ii. Baselined Test Strategy
iii. Transformation design document (where design changes are involved)
iv. Updated Data Models and DDL scripts
v. Transformed and tested Code
vi. Migrated Data
vii. Deployment scripts for the defined target environment
viii. Test Execution Results
ix. Release Document
x. Bug and Fix report
xi. Updated Technical documentation
xii. Performance benchmark

## WBS - Generic
This is the standard list of tasks applicable for the various services.
It also indicates if the individual tasks are done onshore or offshore.
Some tasks have been marked as optional as they may not apply to all services.
|  |  | No. of drivers | Offshore | Onshore
Phase | Tasks | Resource Level | Onsite | Offshore
Knowledge Transfer | Application Walkthru | Level-2 | x
Knowledge Transfer | Architecture walkthru | Level-3 | x
Knowledge Transfer | Test Documentation walkthru | Level-2 | x
Knowledge Transfer | Get and review application source code & artefacts (documentation, configuration, build scripts, test cases, etc) | Level-2 | x
Knowledge Transfer | Collect data through Interviews | Level-3 | x
Knowledge Transfer | Conduct additional interviews with the application team (covering architecture, testing methodology, issues) | Level-2 | x
Analyze | Review Current and Target Environments | Level-3 |  | x
Analyze | Setup Analysis environment | Level-2 | x
Analyze | Run Code assessment tools | Level-2 | x
Analyze | Prepare detailed Assessment Report & Estimates | Level-2 |  | x
Plan | Develop Project Definition | Level-3 |  | x
Plan | Configuration planning | Level-2 |  | x
Plan | Develop Test Strategy and Plan | Level-3 |  | x
Plan | Define Acceptance Criteria | Level-3 |  | x
Plan | Review Acceptance Criteria | Level-3 |  | x
Plan | Review Test Strategy and Plan | Level-3 |  | x
Prepare | Resource Mobilization and onboarding | Level-3 |  | x
Prepare | Create Baselines | Level-2 |  | x
Prepare | Assess Capacity Required | Level-3 |  | x
Prepare | Factory Training to new resources | Level-3 |  | x
Prepare | Set Up Environment | Level-2 |  | x
Design | Create/Refine target Application and Deployment Architecture | Level-3 |  | x
Design | Create Transformation Architecture | Level-3 |  | x
Design | Design Configuration Changes | Level-2 |  | x
Design | Application Transformation Design | Level-2 |  | x
Design | Caching Transformation Design | Level-2
Design | Develop detail design for target (optional based on service) | Level-2
Design | Develop data migration strategy & plan (optional based on service) | Level-2
Build-Configure | Perform Configuration Changes for Applications, Application servers, databases | Level-2
Build - Refactor | Perform Refactor, remediation or recompile code | Level-3
Build - Refactor | Review refactored code | Level-2
Build - Unit Test | Develop unit test plans | Level-2
Build - Unit Test | Complete unit testing | Level-1
Build - Data Prep | Data Masking (optional based on service) | Level-1 | X
Prepare Test Environment | Prepare Test Environment | Level-2
Regression Testing | Develop test plans & test cases (if needed) | Level-2
Regression Testing | Document test results | Level-3
Regression Testing | Analyze Defects | Level-2
Regression Testing | Fix Defects | Level-1
Performance Testing | Define Test Scenarios Optional) | Level-2
Performance Testing | Prepare Test Data (Optional) | Level-1
Performance Testing | Execute Test Cases (Optional) | Level-1
Performance Testing | Analyze Defects (Optional) | Level-3
Performance Testing | Fix Defects | Level-2
Performance Testing | Document Test Results | Level-1
Security Testing | Define Test Scenarios (Authentication & Authorization) - Optional | Level-2
Security Testing | Prepare Test Data (optional) | Level-2
Security Testing | Execute Test Cases (optional) | Level-1
Security Testing | Analyze Defects (optional) | Level-2
Security Testing | Fix Defects (Optional) | Level-1
Security Testing | Document Test Results (Optional) | Level-1
UAT | UAT Environment Support | Level-1
UAT | UAT Support | Level-1
Release | Create Deployment Scripts and Descriptors, Container images if any | Level-2
Release | Package Release prepartion | Level-2
Release | Prepare Release Notes | Level-2
Release | Provide deployment instructions | Level-2
Release | Provide any specific operational guidance | Level-2
Release | Support production readiness review | Level-2
Release | Support delivery of production ready code | Level-1
Release | Support deployment of application/database to production | Level-2
Release | Complete data migration (optional based on service) | Level-1
Release | Acceptance and Signoff | Level-3
Release | Provide post-release report | Level-2
Release | Update Configuration Management database | Level-2
Release | Client transition activities | Level-3
Release | Assemble and deliver materials for knowledge transfer | Level-2
Release | Provide warranty support during Warranty Period (Optional) | Level-1
Project Close | Conduct and document lessons learned session(s) | Level-3
Project Close | Compile Metrics and feedback to Solution and Assessment processes and tools | Level-2
Project Close | Support Project Close-out activities | Level-1

## Assum&WBS-COTS
Assumptions
S# | COTS Application Scope Assumptions
1 | Migration does not involve any type of changes in the COTS application components
2 | The COTS products in scope will exclude all COTS products that are enterprise solutions or have extensive customization features and complex architecture such as SAP, Oracle e-Biz solution, Microsoft Dynamics, SaaS products, Business Intelligence products, Content management products, B2B Comerce solutions, Industry focused solutions such as Cerner, Guidewire etc. There are exclusive practice teams who will be involved in the migration of such products and migration efforts widely vary depending on the extent of customization and other business process and technical integration needs. So such products are not in the scope of this estimation model
3 | COTS vendor will carryout the migration of application components, and deploy the application in each environment - testing, UAT, production etc.
4 | DXC will only manage the implementation, and also if needed will carryout System Integration
5 | COTS migration does not involve any functionality changes, the functionality will be migrated like-for-like
6 | COTS vendor will also perform the manual remediation, including interface connectivity parameters hardcoded in application code. No other type of code changes will be done.
7 | In case the COTS application is not compatible to the target environment (even after version upgrades), COTS vendor will recommend a suitable replacement. DXC will provide inputs if requested.
8 | In case COTS vendor recommends a replacement, client will evaluate the replacement and provide necessary approvals to COTS vendor. DXC will provide inputs if requested.
9 | DXC or COTS vendor will not prepare data for any type of test. Client will provide the test data of production standards (including unit / smoke test)
10 | Client will ensure the COTS vendor takes the ownership of migrating the COTS application. If COTS vendor is not migrating the application, the approach need to be revisited and re-estimated
11 | Migration does not involve performance tuning. Migrated applications will perform atlesast similar to current applications
12 | Client will coordinate with the stake holders of migration implementation, like internal application owners, external trading partners, and ensure their timely participation and contribution
Phase | Tasks | Resource Level | Vendor/DXC | Onsite | Offshore
Knowledge Transfer | Application Walkthru | Level-2 | Vendor/DXC | x
Knowledge Transfer | Architecture walkthru | Level-3 | Vendor/DXC | x
Knowledge Transfer | Test Documentation walkthru | Level-2 | Vendor | x
Knowledge Transfer | Get and review application source code & artefacts (documentation, configuration, build scripts, test cases, etc) | Level-2 | Vendor | x
Knowledge Transfer | Collect data through Interviews | Level-3 | Vendor/DXC | x
Knowledge Transfer | Conduct additional interviews with the application team (covering architecture, testing methodology, issues) | Level-2 | Vendor/DXC | x
Analyze | Review Current and Target Environments | Level-3 | Vendor/DXC |  | x
Analyze | Prepare detailed Assessment Report & Estimates | Level-2 | Vendor/DXC |  | x
Plan | Develop Project Definition | Level-3 | DXC |  | x
Plan | Configuration planning | Level-2 | DXC |  | x
Plan | Develop Test Strategy and Plan | Level-3 | Vendor | x
Plan | Define Acceptance Criteria | Level-3 | Vendor/DXC/Client |  | x
Plan | Review Acceptance Criteria | Level-3 | DXC/Client |  | x
Plan | Review Test Strategy and Plan | Level-3 | DXC/Client |  | x
Prepare | Resource Mobilization and onboarding | Level-3 | Vendor | x
Prepare | Create Baselines | Level-2 | Vendor | x
Prepare | Set Up Environment | Level-2 | Vendor | x
Design | Create/Refine target Application and Deployment Architecture | Level-3 | Vendor | x
Design | Create Transformation Architecture | Level-3 | Vendor | x
Design | Design Configuration Changes | Level-2 | Vendor | x
Design | Application Transformation Design | Level-2 | Vendor | x
Design | Develop data migration strategy & plan (optional based on service) | Level-2 | Vendor | x
Build-Configure | Perform Configuration Changes for Applications, Application servers, databases | Level-2 | Vendor | x
Build - Unit Test | Develop unit test plans | Level-2 | Vendor | x
Build - Unit Test | Complete unit testing | Level-1 | Vendor | x
Build - Data Prep | Data Masking (optional based on service) | Level-1 | Vendor | x
Prepare Test Environment | Prepare Test Environment | Level-2 | Vendor | x
Regression Testing | Develop test plans & test cases (if needed) | Level-2 | Client/DXC Testing Services team |  | x
Regression Testing | Document test results | Level-3 | Client/DXC Testing Services team |  | x
Regression Testing | Analyze Defects | Level-2 | Vendor | x
Regression Testing | Fix Defects | Level-1 | Vendor
Performance Testing | Define Test Scenarios Optional) | Level-2 | Client/DXC Testing Services team |  | x
Performance Testing | Prepare Test Data (Optional) | Level-1 | Client/DXC Testing Services team |  | x
Performance Testing | Execute Test Cases (Optional) | Level-1 | Client/DXC Testing Services team |  | x
Performance Testing | Analyze Defects (Optional) | Level-3 | Client/DXC Testing Services team |  | x
Performance Testing | Fix Defects | Level-2 | Vendor | x
Performance Testing | Document Test Results | Level-1 | Vendor | x
Security Testing | Define Test Scenarios (Authentication & Authorization) - Optional | Level-2 | Client/DXC Testing Services team
Security Testing | Prepare Test Data (optional) | Level-2 | Client/DXC Testing Services team
Security Testing | Execute Test Cases (optional) | Level-1 | Client/DXC Testing Services team
Security Testing | Analyze Defects (optional) | Level-2 | Vendor | x
Security Testing | Fix Defects (Optional) | Level-1 | Vendor | x
Security Testing | Document Test Results (Optional) | Level-1 | Client/DXC Testing Services team
UAT | UAT Environment Support | Level-1 | Vendor | x
UAT | UAT Support | Level-1 | DXC/Vendor
Release | Create Deployment Scripts and Descriptors, Container images if any | Level-2 | Vendor | x
Release | Package Release prepartion | Level-2 | Vendor | x
Release | Prepare Release Notes | Level-2 | Vendor | x
Release | Provide deployment instructions | Level-2 | Vendor | x
Release | Provide any specific operational guidance | Level-2 | Vendor | x
Release | Support production readiness review | Level-2 | Vendor | x
Release | Support delivery of production ready code | Level-1 | Vendor | x
Release | Support deployment of application/database to production | Level-2 | Vendor | x
Release | Complete data migration (optional based on service) | Level-1 | Vendor | x
Release | Acceptance and Signoff | Level-3 | Client
Release | Provide post-release report | Level-2 | DXC/Vendor |  | x
Release | Update Configuration Management database | Level-2 | DXC |  | x
Release | Client transition activities | Level-3 | Vendor | x
Release | Assemble and deliver materials for knowledge transfer | Level-2 | Vendor | x
Release | Provide warranty support during Warranty Period (Optional) | Level-1 | Vendor | x
Project Close | Conduct and document lessons learned session(s) | Level-3 | DXC |  | x
Project Close | Compile Metrics and feedback to Solution and Assessment processes and tools | Level-2 | DXC |  | x
Project Close | Support Project Close-out activities | Level-1 | DXC |  | x

## WBS - Java
Phase | Tasks | Resource Level | Onsite | Offshore
Build - Refactor | Web Service Integration | Level-1
Build - Refactor | MVC Integration | Level-1
Build - Refactor | Application Server Transformation | Level-2
Build - Refactor | ORM Technology Integration | Level-2
Build - Refactor | ORM Technology Transformation- Entity Classes | Level-2
Build - Refactor | ORM Technology Transformation- DAO Classes | Level-2
Build - Refactor | Security Integration | Level-1
Build - Refactor | Transaction Integration | Level-1
Build - Refactor | Caching Transformation | Level-2
Build - Refactor | JMS Messaging Integration | Level-2
Build - Refactor | Scheduling Integration | Level-1
Build - Refactor | JavaMail Integration | Level-1
Build - Refactor | JMX Transformation | Level-1
Build - Refactor | JasperReports Integration | Level-1
Build - Refactor | HTML5 Compliance - mobile | Level-1
Build - Refactor | REST Integration | Level-1
Build - Refactor | Transformation of Stateful EJB | Level-1
Build - Refactor | Transformation of CMP Entity Beans (only for EJB 2.x) | Level-1
Build - Refactor | Manual work post Transformation of MDBs by QTE | Level-1
Build - Refactor | Manual work post Transformation of Stateless (BMT & CMT), BMP and CMP(3.x) EJBs by QTE | Level-1
Build - Refactor | Transformation of CMR Relationships | Level-1
Build - Refactor | Transformation of EJBQL- for CMP Entity beans | Level-1
Build - Refactor | Transformation of EJB Authorization Code | Level-1
Build - Refactor | Code review for CMT & BMT beans | Level-2
Build - Refactor | Overall Spring Configuration changes to be done
Build - Refactor | Build and Packaging of Spring code base
Build - Refactor | Spring Insight review of deployed Spring war file

## U2L Assum&WBS
2 | U2L Refactor - Java | Simple | Medium | Complex
| Complexity description Please Note: - No upgrades for TPL like spring, hibernate, struts etc (for U2L - Java) - No architecture changes. Lift and shift with minor changes to code / configuration will be done to suit the target environment - Source Linux versions include RHEL 4 or above and Ubuntu 14 or above - Source Legacy Unix versions include Solaris 10 and above Any app not conforming to above criteria need to be assessed on case-by-case basis and migration track and approach devised accordingly | - Linux to Linux migration with same Linux versions on source and target - Same Java JDK versions on source and target - up to 30 programs or screens (each with around 20 fields and 3 lookups) - Single Server, single tier application -Database Tables: 0-100 -Interfaces 0 - 5 (each with 2 integration touch points such as FTP, Message Que. Other integrations need to be assessed on case by case basis) -Business complexity: Medium / Complex | - Linux to Linux migration with same or different Linux versions on source and target -Same Java JDK versions on source and target - 31-100 programs or screens (each with around 20 fields and 3 lookups) - Single server, single or multi-tier application -Database Tables: 101-200 -Interfaces 6 - 10 (each with 2 integration touch points such as FTP, Message Que. Other integrations need to be assessed on case by case basis) -Business complexity: Medium / Complex | -Legacy Unix to Linux migration - Older Java JDK (less than 6) versions on source and target - 100-250 programs or screens (each with around 20 fields and 3 lookups) - Multi-server, single or multi-tier application -Database Tables: 201-350 -Maximum of 15 Interfaces (each with 2 integration touch points such as FTP, Message Que. Other integrations need to be assessed on case by case basis) -Business complexity: Medium / Complex
2 | U2L Refactor - Non Java
| Complexity description Please Note: - No upgrades for any TPL eg boost, RW etc - No incompatible OS/Kernel/Compiler/ Memory dependent source code - No architecture changes. Lift and shift with minor changes to code / configuration will be done to suit the target environment - Source Linux versions include RHEL 4 or above and Ubuntu 14 or above - Source Legacy Unix versions include Solaris 10 and above Any app not conforming to above criteria need to be assessed on case-by-case basis and migration track and approach devised accordingly | - Linux to Linux migration with same Linux versions on source and target - Non Java technologies like (C/C++, Perl) - No change required to the compiler or runtime - up to 30 programs or screens (each with around 20 fields and 3 lookups) -Single Server, single tier application -Database Tables: 0-100 -Interfaces 0 - 5 (each with 2 integration touch points such as FTP, Message Que. Other integrations need to be assessed on case by case basis) -Business complexity: Medium / Complex - approx 45 Test Cases | - Linux to Linux migration with same or different Linux versions on source and target - Non Java technologies like (C/C++, Perl) - No change required to the compiler or runtime - 31-100 programs or screens (each with around 20 fields and 3 lookups) - Single server, single or multi-tier application -Database Tables: 101-200 -Interfaces 6 - 10 (each with 2 integration touch points such as FTP, Message Que. Other integrations need to be assessed on case by case basis) -Business complexity: Medium / Complex - approx 45 Test Cases | - Unix to Linux migration - Non Java technologies like (C/C++, Perl) - Changes required to the compiler or runtime - 100-250 programs or screens (each with around 20 fields and 3 lookups) - Multi-server, single or multi-tier application -Database Tables: 201-350 -Maximum of 15 Interfaces (each with 2 integration touch points such as FTP, Message Que. Other integrations need to be assessed on case by case basis) -Business complexity: Medium / Complex - approx 45 Test Cases
# | Activity | Tasks | Resource | CSC Resource | Responsibility
1 | Assess | Setup Assessment Environment | System / Technical Support | System Administrator | DXC
2 | Assess | Run Assessment Tools | Architect | Architect | DXC
3 | Assess | M3 - System Requirements Package | Architect | Architect | DXC
4 | Prepare | Develop Project Definition | Project Manager | Project Manager | DXC
5 | Prepare | Configuration planning | System / Technical Support | Configuration Manager | DXC
6 | Prepare | Develop Test Strategy and Plan | System / Technical Support | Senior Tester | DXC
7 | Prepare | Define Acceptance Criteria | Project Manager | Project Manager | DXC
8 | Prepare | Review Acceptance Criteria | Project Manager | Project Manager | DXC, Client
9 | Prepare | Review Test Strategy and Plan | System / Technical Support | Senior Tester | DXC, Client
10 | Prepare | Project Preparation | Project Manager | Project Manager | DXC
11 | Prepare | Create Baselines | System / Technical Support | Configuration Manager | DXC
12 | Prepare | Assess Capacity Required | Project Manager | Project Manager | DXC
13 | Prepare | Set Up Development Sandbox | System / Technical Support | System Administrator | DXC, Client
14 | Design | HLD - Target Application Architecture | Architect | Architect | DXC
15 | Design | HLD - Target Infrastructure Architecture | Architect | Architect | DXC
16 | Design | Data Migration Strategy & Plan | Database Administrator (DBA) | Database Administrator (DBA) | DXC
17 | Design | Data Migration - UNLOAD | Database Administrator (DBA) | Database Administrator (DBA) | DXC
18 | Design | Data Migration - LOAD | Database Administrator (DBA) | Database Administrator (DBA) | DXC
19 | Design | M5 - Design Package | Architect | Architect | DXC
20 | Build - Rehost | Complete Data Migration | Database Administrator (DBA) | Database Administrator (DBA) | DXC
21 | Build - Rehost | Shell Script Migration | Developer | Developer | DXC
22 | Build - Rehost | Change Runtime on Target OS | System / Technical Support | Senior Developer | DXC
23 | Build - Rehost | Module Installation | System / Technical Support | Senior Developer | DXC
24 | Build - Rehost | Resolve Hardcoded IP address, host names, paths | Developer | Developer | DXC
25 | Build - Rehost | Resolve Compiler Issues | Developer | Developer | DXC
26 | Build - Rehost | Resolve Standard Library Issues | Developer | Developer | DXC
27 | Build - Rehost | Validate Endianness | Developer | Developer | DXC
28 | Build - Rehost | Resolve Threading Issues | Developer | Developer | DXC
29 | Build - Rehost | Validate 32/64 bit variations | Developer | Developer | DXC
30 | Build - Rehost | Resolve Internationalization Issues | Developer | Developer | DXC
31 | Build - Rehost | Resolve OS Calls | Developer | Developer | DXC
32 | Build - Rehost | Resolve Memory Management Issues | Developer | Developer | DXC
33 | Build - Rehost | Resolve Platform Specific Modules | Developer | Developer | DXC
34 | Build - Rehost | Resolve 3rd party components / Libraries with OS/Server dependencies | Developer | Developer | DXC
35 | Build - Rehost | Resolve Database Variations | Database Administrator (DBA) | Database Administrator (DBA) | DXC
36 | Build - Rehost | Interface Integration (Medium) | System / Technical Support | Senior Developer | DXC
37 | Build - Rehost | Interface Integration (Complex) | System / Technical Support | Senior Developer | DXC
38 | Build - Rehost | Additional PM Tasks | Project Manager | Project Manager | DXC
39 | Build - Rehost | Other Tasks | System / Technical Support | Senior Developer | DXC
40 | Build - Rehost | Environment Validation - Batch | System / Technical Support | System Administrator | DXC
41 | Build - Rehost | Environment Validation - Online | System / Technical Support | System Administrator | DXC
42 | Build - Rehost | Environment Validation - Reporting | System / Technical Support | System Administrator | DXC
43 | Build - Rehost | Database Validation | Database Administrator (DBA) | Database Administrator (DBA) | DXC
44 | Build - Rehost | Environment Validation - Tools | System / Technical Support | System Administrator | DXC
45 | Prepare Test Environment | Prepare Test Environment | System / Technical Support | System Administrator | DXC, Client
46 | Testing | Testing | System / Technical Support | Senior Tester | DXC
47 | Testing | Testing | Quality / Tester | Quality / Tester | DXC
48 | Testing | Analyze Defects | System / Technical Support | Senior Developer | DXC
49 | Testing | Fix Defects | Developer | Developer | DXC
50 | Performance Testing | Define Test Scenarios / Test Scripts | System / Technical Support | Senior Tester | DXC
51 | Performance Testing | Prepare Test Data | Quality / Tester | Quality / Tester | DXC
52 | Performance Testing | Execute Test Cases | Quality / Tester | Quality / Tester | DXC
53 | Performance Testing | Analyze Defects | System / Technical Support | Senior Developer | DXC
54 | Performance Testing | Fix Defects | Developer | Developer | DXC
55 | Performance Testing | Document Test Results | System / Technical Support | Senior Tester | DXC
56 | UAT Support | Environment Support | System / Technical Support | System Administrator | DXC, Client
57 | UAT Support | Analyze Defects | System / Technical Support | Senior Developer | DXC
58 | UAT Support | Fix Defects | Developer | Developer | DXC
59 | Release | Create Deployment Scripts and Descriptors | System / Technical Support | Senior Developer | DXC
60 | Release | Package Release prepartion | System / Technical Support | Senior Developer | DXC
61 | Release | Prepare Release Notes | System / Technical Support | Senior Developer | DXC
62 | Release | Acceptance and Signoff | Project Manager | Project Manager | DXC
63 | Release | Production Deployment Support | System / Technical Support | System Administrator | DXC, Client
64 | Release | Client transition activities | Architect | Architect | DXC

## WBS-Database
# | Activity | Tasks | Resource
1 | Prepare | Database Walkthrough | Level-3
2 | Prepare | DB Documentation Walkthrough | Level-3
3 | Prepare | Assess Capacity Required | Level-3
4 | Prepare | Set Up Environment | Level-3
5 | Plan | Develop Project Definition | Level-3
6 | Plan | Develop Project Plan and Schedule | Level-3
7 | Plan | Configuration planning | Level-3
8 | Plan | Develop Test Strategy and Plan | Level-2
9 | Plan | Define Acceptance Criteria | Level-2
10 | Discover | Analyze Database Architecture | Level-2
11 | Discover | Analyze database schemas | Level-2
12 | Discover | Analyze database storages | Level-2
13 | Discover | Analyze db batch processes | Level-2
| Discover | Analyze application impact | Level-2
14 | Design | Database | Level-2
15 | Design | Database schemas | Level-2
16 | Design | Database Storages | Level-2
17 | Design | Business rules for batch processes | Level-2
18 | Design | Technical specification document | Level-2
19 | Design | Data Validation document | Level-2
20 | Design | Datamodel | Level-2
21 | Design | Data Migration | Level-2
| Design | Application Changes | Level-2
22 | Build | Database Scripts | Level-1
23 | Build | Storage scripts | Level-1
24 | Build | Schemas Scripts | Level-1
25 | Build | Table Scripts | Level-1
26 | Build | View Scripts | Level-1
27 | Build | Procedure Scripts | Level-1
28 | Build | Function Scripts | Level-1
29 | Build | Trigger Scripts | Level-1
30 | Build | Data Extract Scripts | Level-1
31 | Build | Data Load Scripts | Level-1
32 | Build | Set-up DB Environment | Level-2
| Build | Application Changes | Level-1
33 | Test | DB Environment | Level-1
34 | Test | Scripts - DB, Schema, Table, view, Trigger, Procedue, Function & Package | Level-1
35 | Test | Data Extract | Level-2
36 | Test | Data load | Level-2
37 | Test | Validate data | Level-2
38 | Release | Create deployment package | Level-2
39 | Release | Prepare Release Notes | Level-2
40 | Release | Acceptance and Signoff | Level-2
41 | Release | Client transition activities | Level-2
Note on C12: Includes assigning business names to varibles,diclarations and tags to the COBOL program in Modernization workbench
Note on C17: Author: Includes assigning business names to fields,diclarations of Screen in Modernization Workbench
Note on C18: Author: Includes assigning business names to fields,diclarations of table in Modernization Workbench

## LN to O365
S# | Lotus Notes Applications Scope Assumptions
| Complexity Category | Complexity Definition parameters and values | [7 empty] | Remarks
|  | LN DB Size | No of NSF Files | No of Fields | No of Scripts | View/Forms/Screens | Workflows/ Business rules/ Customization | Webservices | No of Documents
1 | Simple | <=5 GB | 1 | 150 | <=5 | <= 8 | NA | None | 20000 | 1. View/Forms are built with O365 Sharepoint out of the box (OOB) features 2. script includes - simple database script count, simple Agent count, simple script library count, profile docs count
2 | Medium | >5 GB and <= 10 GB | 1 | 250 | <=10 | <=12 | NA | None | 50000 | 1. View/Forms are compatible with default O365 forms and no customization to O365 forms 2. script includes - simple database script count, simple Agent count, simple script library count, profile docs count
3 | Complex | >10 GB and <= 15 GB | 1 | 500 | <=15 | Forms <= 8 and Views <= 12 | Designer workflows with 2 levels of approval | None | 200000 | 1. View/Forms are built with O365 Sharepoint out of the box (OOB) features 2. script includes - database script count, Agent count, script library count, profile docs count 3. Workflows: Designer based workflow
1 | Any redundant/unused content to be cleared in source system before migration by the application owners.
2 | No changes to be done on documents / attachments being migrated
3 | Administrator restricted file types will not be moved to Office 365 (.EXE, MP3 etc. if restricted by Client administrators)
4 | User creation / provisioning in O365 is not included as part of the effort
5 | Formatting of the content in rich text boxes by the tool is aligned on the target platform. If the alignment is not proper for a given application, it has to be taken up on case by case basis separately.
6 | The look and feel of the target applications will not be the same as in Louts Notes due to platform restrictions.
7 | Data will be extracted from Lotus Notes in CSV format. Client will do the import and building the functionality.
8 | If an application is found to be not compatible for planned migration approach and the target technology, the target technology, approach and estimation will be revised on case-by-case basis.
Weightages
| DB Size |  | 30%
| No. of forms/screens |  | 40%
| Workflows |  | 20%
| Multi-location |  | 5%
| Document Avl |  | 5%

## Assumption Table
List of Assumptions
# | Title | Description | Remarks
1 | Application and Infrastructure information - Source infrastructure | The current estimate is based on the information provided by <client> in <document>. If version numbers are not provided, we assume the software is of the latest or latest - 1 version. | Mandatory assumption if software versions are not provided.
2 | Migration Complexity & treatment | The treatment and complexity of the migration is estimated based on the information provided in <document> and will be re-assessed during the detailed assessment. Any substancial change (> 5%) in the complexity & treatment distribution will result in an adjustment of the effort and price. | Mandatory assumption if you have not done a detailed assessment previously.
3 | Availability of Application artefacts | All components of the application are completely available upon request to the delivery team. This includes source code (for Source Code Migration, Remediation and Recompilation), the documentation, the binaries, the scripts, the libraries and any other component required to migrate/transform the application. | If this cannot be guaranteed by the client, you will have to add extra time to coordinate the collection of the artifacts. Either you increase the project management percentage (e.g. by 10%) or the effort by treatment through the effort variation. (See note at the bottom)
4 | Testing | Only unit testing, smoke testing and support for Acceptance testing has been included covering major business flows. Effort for defect fixes included. | For any other testing, efforts need to be estimated separately.
| Functional Equivalence/Like for Like | While applications may be refactored or remediated in order to upgrade to latest versions or specifications, functional equivalence will be strictly maintained. No functional enhancements have been included in these estimates. | Any enhancements will need to be separately estimated and priced. It is preferrable to implement enhancements after the migration/modernization is completed.
5 | Availability of application litterate people | Client will ensure Application owners/SMEs / COTS vendors / external partners will be available through out the project for clarifications, discussions, as required (specific requirement will be identified during initiation phase and circulated to the stake holders). | If this cannot be guaranteed by the client, you will have to add extra time to coordinate the collection of the artifacts. Either you increase the project management percentage or the effort by treatment through the effort variation. (See note at the bottom)
6 | LDAP configuration/Integration and Single Sign-on configurations, integrating eternal Authentication and Authentication systems | Efforts for LDAP and Single-sign-onintegration/configuration is not included in these estimates. Also, integrating with or configuring external autnentication and authorization systems have not been included in these efforts | These configurations and integrations are assumed to be performed by infrastructure teams and efforts and plan for the same will need to be provided by infrastructure teams
7 | Integration of current and future environment | The source landscape and target landingzones are available and connected through a secure connection (e.g. Wlan, Vlan). Minimal bandwith required will be defined during the assessment. The <client> operations team is responsible for design, build, test and RUN of current and future environment. | This assumption is required.
8 | Certificate and other security features | At the moment the pricing assumes no certificates, encryption mechanisms or other security features are used. This assumption will be assessed during assessment and effort may be adapted. | These are performed by infrastructure teams (either DXC or client teams) and hence efforts will be estimated as per their estimation models/approaches and added to total estimates.
9 | Inputs from clients | Current baselined Source code Access to development and test environments Current baselined design documents Target Architecture details Test plan, test cases and test data Production support/operations manual | If any of these are not available, efforts need to be included. The model provides for specifying test case availability but other documents are not addressed and have to be estimated separately.
10 | Firewall rules | Assessing and changing firewall rules are the responsibility of infrastructure teams and hence are not included here. | Please contact infrastructure teams to include these efforts if they are in scope
11 | File/Print Server | These migrations are the responsibility of infrastructure teams and are not included here | Please contact infrastructure teams to include these efforts if they are in scope
12 | Latency | In case all applications that are integrated or the accessed databases cannot be migrated in the same wave, latency between servers and environments must be such that no delays are introduced in the communication between both applications and/or with associated databases. | Mandatory assumption. In case we encounter significant latencies, the impacts will be assessed and efforts recalculated accordingly
13 | Applications not in scope | Any dependencies with applications not in scope, will be defined upfront during design or source to target mapping exercise. <Client> will ensure the availablity of those applications during the migration process. Resources litterate with those applications will be available to support the migration team. | Mandatory assumption
14 | Infrastructure | Availability, connectivity,(admin-or sufficient priviliges) access bandwith capacity, security for remote DXC staff to perform all treatments over Clients Network (Image migration requiring sufficient bandwitdh) | Mandatory assumption
15 | Remote staff | DXC remote staff (India, Malaysia, Philipines, Poland, Bulgaria, etc) to access all required IT infrastructure to perform scope (assessment and migration treatments.) Client to manage security and compliancy (regulations). All communication and documentation to be in English. Scope can be delivered from offshore location, only minimal local DXC staff required, requiring limited travel | Mandatory assumption
16 | Tools | Each track is associated with code assessment and transformation tools, life cycle management tools that go along with establishing the factory line for the customer. If customer wants to use their own processes or tools, the effort to customize and plug in those processes and tools will be reworked. It is important for clients to allow DXC tools to be deployed in their envieonments through a due approval process. | Mandatory assumption, particularly important if you use UD as UD may require the installation of agents on the network, which can cause issues with the client security team.
17 | Server Image Migration | This will be in scope of infrastructure team and is not covered in the factory tracks for Application Services | Mandatory assumption
18 | Client skills, knowledge and capacity | Client able to perform all planned activities in time. The timeframe is set by the project management office. | Mandatory assumption
19 | Application Installation | A single installation script can be used for all environments: Dev, Test, Acceptance and Production. We assume the same code (source & binary where applicable) is used for all installations. Any special deployment components such as Docker images have not been included in these efforts. Also, it is assumed that the application team will only deploy the application and rest of the web server, application and database software will be deployed by the infrastructure team and will need to be estimated separately. | If the applications that are installed in Dev, Test, Acceptance and Production are not exactly the same and/or cannot be installed with a single script, consider them as separate applications in the effort estimation. Please contact infrastructure teams for estimates as mentioned.
20 | Deployment in Production | The actual deployment in production is performed by the client operations team. | If we have to deploy in production, please include additional time taking into account the release cycle of the client. This is done as described in the note here under.
21 | Source code Baseline | Estimates are made based on the current status of code that will be baselined at the start of the project. | Any later changes in code versions will be considered thru change process.
22 | Documentation language | Documentation and comments embedded in scripts and source code are assumed to be in English | If other languages are used, first consider if you can deliver parts of the service from a nearshore location where appropriate language skills are available. If this is not the case, add additional effort for translation using the approach in the note here under.
23 | Commercial off the Shelf applications | For COTS applications, the application is only re-installed if the current version is supported in the target environment and deployment appliance is available. In case an upgrade is required, a version of the COTS application that is supported in the target environment needs to be available. The redevelopment of any customization for the upgraded application is not included. Potential database reconfigurations are not included either. | SAP and other major COTS applications are not included in this estimation. They should be estimated by the appropriate practice. Smaller application packages are re-installed as-is.
24 | Database Upgrades/Migrations | We assume the databases are either Oracle/Sybase/MSSQL/MySQL databases. We also assume their version to be n-1 or n. We assume that all database or data migration are handled over the network. | If other databases are used, make sure you have resources available with the appropriate database experience. As these resources are scarce, you will need to warn delivery early.
25 | Number of database migrations | We assume an average of 1 database per application. We assume the content of the database is migrated twice, once for testing purposes and once during cut-over. Only as-is migration without adding any new data objects or data design
26 | Environments | Any hardening activities or monitoring agents specific to OS/Server or Application is assumed to be part of cloud build and not in the scope of treatment teams. | Mandatory assumption
27 | Integration | DXC is not responsible for installing or reconfiguring any integration tools in the external and partner systems. Also, DXC is not responsible to make any cnahges to the code or design of these external systems

## TO DO
1 | Validate the Complexity Model and estimates through data from Aon | Done
2 | Calculate confidence level of estimates based on inputs | To do
3 | Create a button to prepare input rows for data entry | To do
4 | Integrate with staffing model, skills, build ramp up models and visualization | To do

## Inputs from Guru (hidden)
| Weeks | Fte
Simple | 3 | 2 | 240
m | 5 | 2 | 400
c | 8 | 2 | 640

## Resource loading (hidden)
Pizza teams
|  | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01
[33 empty] | sum |  | reqd
#REF! | Win 2003 or older to Win 2012 | 2 | 2 | 4 | 4 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 5 | 4 | 3 | 3 | 3 | [6 empty] | 150 |  | #REF! | 206400
#REF! | Unix to Linux (U2L) - Java | 1 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | [6 empty] | 75 |  | #REF! | 103200
#REF! | Unix to Linux (U2L) - non-Java | [31 empty] | 25 |  | #REF! | 34400 | bar: 2017-06-01 to 2019-06-01
#REF! | Manual Migration | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 50 |  | #REF! | 68800
#REF! | Lift & Shift - Outliers | 1 | 1 | 2 | 2 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | [8 empty] | 75 |  | #REF! | 103200
#REF! | Packaged Apps | 1 | 2 | 2 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 1 | 1 | [10 empty] | 75 |  | #REF! | 103200
| 2 pizza box teams | 7 | 9 | 13 | 16 | 21 | 22 | 25 | 25 | 27 | 27 | 27 | 27 | 26 | 24 | 24 | 21 | 21 | 19 | 16 | 13 | 11 | 9 | 8 | 6 | 6 | [6 empty] | 450 |  | #REF! | 619200
| total FTEs deployed | 56 | 72 | 104 | 128 | 168 | 176 | 200 | 200 | 216 | 216 | 216 | 216 | 208 | 192 | 192 | 168 | 168 | 152 | 128 | 104 | 88 | 72 | 64 | 48 | 48
| total hrs | 9632 | 12384 | 17888 | 22016 | 28896 | 30272 | 34400 | 34400 | 37152 | 37152 | 37152 | 37152 | 35776 | 33024 | 33024 | 28896 | 28896 | 26144 | 22016 | 17888 | 15136 | 12384 | 11008 | 8256 | 8256
#REF! | Apps migrated per month | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | <- total apps
17% | Savvis | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
83% | Harborside | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Assumptions (hidden)
1 | total number of applications are only business applications and do not include infra applications and tools
2 | the starting point of the model is #s for servers, apps and databases. It is assumed that these numbers are available in a given pursuit. Incase not, we can assume any missing item from the ratio of this model portfolio.
3 | in absence of app zero license, we can consider this number for a standard rehost category of efforts and that set of #s should be distributed in refactory category (across various use cases listed therien)
4 | also it is assumed that all COTS migration are feasible, and incase there are exception those would be dealt on case on case basis. Also the efforts for alternate solution would be arrived at during execution phase in consultation with the COTS vendor
5 | all upgrade scenarios are covered in respective use case complexities. For eg, U2L which also requires WAS to JBOSS migration would probably be classified as complex. Incase it is a stated need from the client that WAS to JBOSS is needed across inventory, we should accordingly adjust the % distribution