## 3-Point Estimates (hidden)
Treatment ↓ / Complexity Factor → | Simple (person hours) | Medium (person hours) | High (person hours)
Windows to Windows Migration | 490 | 900 | 1480
Unix to Linux (U2L) - Java | 180 | 240 | 1140
Unix to Linux (U2L) - Other Technologies | 610 | 730 | 1060
Binary Application Migration |  | 240
Packaged Application Migration | 60 |  | 1200
Note: Any parameters beyond the range given below need to be assessed on case-by-case basis and estimated
Contains all activities, including project management
Treatment ↓ / Complexity Factor (effort in person hours) → | Simple | Medium | Complex
Windows to Windows Migration
Windows Platform Upgrade | 200 | 250 | 300
Source 'OS / Platform: | Windows 20012 | Windows 2008 | Windows 2003
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Environments: | 1 | 2,3 | 4,5
Servers: | 1 - Single tiered | 2,3 - Multi-tiered | 4-6 - Multi-tiered with Load balancing and failover
Database tables/Objects | <100 | 100-199 | 200-350
ASP to ASP.NET | 600 | 1200 | 1600
Source 'OS / Platform: | Windows 2012 | Windows 2008 | Windows 2003
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Third Party Components/References | <5 | 5-10 | 11-20
Environments: | 1 | 2,3 | 4,5
Servers: | 1 - Single tiered | 2,3 - Multi-tiered | 4-6 - Multi-tiered with Load balancing and failover
Database tables/Objects | <100 | 100-199 | 200-350
VB.Net to ASP.Net | 795 | 1740 | 2574
Source 'OS / Platform: | Windows 20012 | Windows 2008 | Windows 2003
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Third Party Components/References | <5 | 5-10 | 11-20
Environments: | 1 | 2,3 | 4,5
Servers: | 1 - Single tiered | 2,3 - Multi-tiered | 4-6 - Multi-tiered with Load balancing and failover
Database tables/Objects | <100 | 100-199 | 200-350
MS-Access to ASP.NET | 684 | 1518 | 2389
Source 'OS / Platform: | Windows 2012 | Windows 2008 | Windows 2003
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Third Party Components/References | <5 | 5-10 | 11-20
Environments: | 1 | 2,3 | 4,5
Servers: | 1 - Single tiered | 2,3 - Multi-tiered | 4-6 - Multi-tiered with Load balancing and failover
Database tables/Objects | <100 | 100-199 | 200-350
Upgrade .Net Framework | 847 | 1855 | 2743
Source OS / Platform: | Windows 2012 | Windows 2008 | Windows 2003
.Net Framework version | .Net 3.5 and above | .Net 3.0 and above | .Net 2.0 and above
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Third Party Components/References | <5 | 5-10 | 11-20
Environments: | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
VB to VB.NET or C#.Net | 1000 | 3600 | 6000
OS / Platform: | Windows 2008/2012 | Windows 2003 | Windows 2000
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Third Party Components/References | <5 | 5-10 | 11-20
Environments: | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
CFML to ASP. NET | 887 | 1518 | 2165
OS / Platform: | Windows 2008/2012 | Windows 2003 | Windows 2000
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Third Party Components/References | <5 | 5-10 | 11-20
Environments: | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
Unix to Linux U2L Migration
Linux Platform Upgrade | 200 | 250 | 300
Source OS / Platform: | Same version on source and target | Source Linux versions include RHEL 5 or above or SLES 9 or above. | Source Linux versions include RHEL 4 or above and Ubuntu 14 or above or SLES 8 or above.
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Environments: | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
U2L - Java | 330 | #REF! | #REF!
OS / Platform: | RHEL Linux 5.x,6.x | RHEL Linux 4.x | Unix / Solaris
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Environments: | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
U2L - C, C++, Perl | #REF! | #REF! | #REF!
OS / Platform: | RHEL Linux 5.x,6.x | RHEL Linux 4.x | Unix / Solaris
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Environments: | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
Java Refactor - Java /JEE Version Upgrade
Java /JEE Version | Java EE6, EE7 | Java EE5, J2EE1.4 | J2EE1.3, J2EE1.2
Number of Objects (Screens / Forms / Reports / Programs): | <25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Environments: | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
Third Party Components/References | <5 | 5-10 | 11-20
Java Refactor - Refactor to Spring and Hibernate
Java/JEE Version | Java EE6, EE7 | Java EE5, J2EE1.4 | J2EE1.3, J2EE1.2
Source Framework | Spring, Hibernate lower versions | Struts, DAO | No MVC framework used
Number of Objects (Screens / Forms / Reports / Programs) | <25 | 26-90 | 91-150
Interfaces | 1 | 2,3 | 4,5
Third Party Components/References | <5 | 5-10 | 11-20
Environments | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
Java Refactor - App Server Migration
Java/JEE Version | Java EE6, EE7 | Java EE5, J2EE1.4 | J2EE1.3, J2EE1.2
Number of Objects (Screens / Forms / Reports / Programs) | <25 | 26-90 | 91-150
Interfaces | 1 | 2,3 | 4,5
Third Party Components/References | <5 | 5-10 | 11-20
Environments | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
Lotus Notes Migration
Lotus Notes to Sharepoint O365 | 130 | 265 | 519
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Data Size: | <10 GB | 11-30 GB | 31-50 GB
COTS Migration
COTS Upgrade (migrating to new environment with vendor support) | 100 | 125 | 175
Number of Objects (Screens / Forms / Reports / Programs): | < 25 | 26-90 | 91-150
Interfaces: | <2 | 3-5 | 6-10
Environments | 1 | 2,3 | 4,5
Servers: | <10 GB | 11-30 GB | 31-50 GB
Decommission
Decommission | 207 | 348 | 519
Interfaces: | <2 | 3-5 | 6-10
Environments: | 1 | 2,3 | 4,5
Servers: | 1 | 2,3 | 4-6
Database Migration
DB - MySQL/MS SQL/Postgres/DB2 Upgrade | 115 | 145 | 178
Clustering / # of Nodes: | Standalone Server | Clustered - 2 Nodes | Clustered - 3/4 Nodes
Number of DB Objects: | <100 | 101-300 | 301-500
DB size: | <500 GB | 500 GB - 1 TB | 1 TB - 1.5 TB
DB - Oracle Upgrade | 144 | 233 | 296
Clustering / # of Nodes: | Standalone Server | Clustered - 2 Nodes | Clustered - 3/4 Nodes
Number of DB Objects: | <100 | 101-300 | 301-500
DB size: | <500 GB | 500 GB - 1 TB | 1 TB - 1.5 TB
DB - Vendor Change, Non Cluster | 618 | 1572 | 2471
Number of DB Objects: | <100 | 101-300 | 301-500
DB size: | <500 GB | 500 GB - 1 TB | 1 TB - 1.5 TB
DB - Vendor Change, Clustered (2 Nodes assumed) | 791 | 1784 | 2766
Number of DB Objects: | <100 | 101-300 | 301-500
DB size: | <500 GB | 500 GB - 1 TB | 1 TB - 1.5 TB
Note on A1: 1st iteration base estimates

## Factory Input
Sr.No | Application Name | Migration Factory Line and Sub Track | Source to TargetOS | Business Rule/Workflow/UI | Source to Target Language/ Framework | Source to target DB | Total Complexity | Total Hours
1 | Apps 5
2 | Papperslöst
3 | SPD
4 | EAI
5 | Siebel
6 | Telenor.se
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199

## Model (hidden)
Migration Factory Line | Simple | Medium | Complex | Complex to Simple Ratio | Factory line Group | Source to TargetOS | Business Rule/Workflow/UIComplexity | Source to Target Framework | Source to target DB | App Size Complexity (SLOC, Screens, reports, Scripts) | DB Size/No. of DB Objects | Data Size | No. of 3rd Party Components | No. of Environments | No. of External Interfaces | No. of internal Interfaces | Architecture Complexity | Concurrent users | Location | Internationalization/Localization | Doc /Data Availability | Analysis (including Source Code Analysis) | Design and Planning | Transformation Treatment | Testing | UAT Support | Deployment / Release | Warranty Support | Project Management | Total | Architect/Migration Lead | Sr. Developers | Developer | Test Lead/Test Manager | Sr. Tester | Tester | Build & Deployment Engineer | PM | Total
Windows Upgrade | 200 | 250 | 300 | 1.5 | 1 | 30% | 0% | 0% | 0% | 30% | 5% | 0% | 5% | 10% | 5% | 5% | 5% | 15% | 5% | 15% | 5% | 10% | 10% | 35% | 10% | 5% | 20% | 0% | 10% | 100% | 11.5% | 18.25% | 33.5% | 2% | 4.25% | 6.5% | 14% | 10% | 100%
Linux to Linux | 200 | 250 | 300 | 1.5 | 2 | 30% | 0% | 0% | 0% | 30% | 5% | 0% | 5% | 10% | 5% | 5% | 5% | 15% | 5% | 15% | 5% | 10% | 10% | 35% | 10% | 5% | 20% | 0% | 10% | 100% | 11.5% | 18.25% | 33.5% | 2% | 4.25% | 6.5% | 14% | 10% | 100%
U2L-Java | 330 | 550 | 1045 | 3.1667 | 3 | 20% | 0% | 0% | 0% | 30% | 5% | 0% | 5% | 10% | 10% | 5% | 10% | 15% | 5% | 15% | 5% | 10% | 10% | 45% | 5% | 5% | 15% | 0% | 10% | 100% | 12% | 19.75% | 40% | 1.5% | 2.75% | 3.5% | 10.5% | 10% | 100%
U2L-Others | 824 | 1353 | 1958 | 2.3762 | 3 | 20% | 0% | 0% | 0% | 30% | 5% | 0% | 5% | 10% | 10% | 5% | 10% | 15% | 5% | 15% | 5% | 10% | 10% | 45% | 5% | 5% | 15% | 0% | 10% | 100% | 12% | 19.75% | 40% | 1.5% | 2.75% | 3.5% | 10.5% | 10% | 100%
ASP to .Net | 600 | 1200 | 1600 | 2.6667 | 1 | 5% | 10% | 15% | 0% | 30% | 5% | 0% | 5% | 5% | 10% | 5% | 5% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
VB to .Net | 1000 | 3600 | 6000 | 6 | 1 | 0% | 10% | 0% | 0% | 40% | 5% | 0% | 15% | 5% | 15% | 0% | 5% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
VB.Net to ASP.Net | 795 | 1740 | 2574 | 3.2377 | 1 | 0% | 10% | 15% | 0% | 30% | 5% | 0% | 10% | 5% | 10% | 5% | 5% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
CFML to ASP .Net | 887 | 1518 | 2165 | 2.4408 | 1 | 10% | 10% | 0% | 0% | 30% | 5% | 0% | 10% | 10% | 10% | 5% | 5% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
MS Access to .Net | 684 | 1518 | 2389 | 3.4927 | 0 | 0% | 10% | 15% | 0% | 25% | 15% | 5% | 5% | 5% | 7% | 3% | 5% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
Lotus Notes to O365 | 130 | 265 | 519 | 3.9923 | 8 | 0% | 20% | 0% | 0% | 45% | 0% | 30% | 0% | 0% | 0% | 0% | 0% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
DeCommission | 207 | 348 | 519 | 2.5072 | 4 | 15% | 0% | 0% | 20% | 0% | 30% | 5% | 0% | 15% | 10% | 5% | 0% | 0% | 5% | 0% | 0% | 15% | 15% | 40% | 5% | 5% | 10% | 0% | 10% | 100% | 14% | 22.25% | 38% | 2% | 3.25% | 3.5% | 7% | 10% | 100%
COTS Upgrade | 100 | 125 | 175 | 1.75 | 4 | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 20% | 10% | 15% | 0% | 5% | 0% | 5% | 20% | 15% | 20% | 5% | 5% | 20% | 0% | 15% | 100% | 15% | 21% | 26% | 2.25% | 3.25% | 3.5% | 14% | 15% | 100%
DB Upgrade- MySQL/SQL Server | 115 | 145 | 178 | 1.5478 | 5 | 5% | 0% | 0% | 15% | 0% | 30% | 15% | 0% | 10% | 7% | 3% | 10% | 15% | 5% | 15% | 5% | 10% | 15% | 35% | 5% | 5% | 20% | 0% | 10% | 100% | 12.5% | 20.5% | 34.5% | 1.75% | 3.25% | 3.5% | 14% | 10% | 100%
DB Upgrade - Oracle | 143 | 233 | 296 | 2.0699 | 5 | 5% | 0% | 0% | 15% | 0% | 30% | 15% | 0% | 10% | 7% | 3% | 10% | 15% | 5% | 15% | 5% | 10% | 15% | 35% | 5% | 5% | 20% | 0% | 10% | 100% | 12.5% | 20.5% | 34.5% | 1.75% | 3.25% | 3.5% | 14% | 10% | 100%
Cross DB Migration - Non Cluster | 618 | 1572 | 2471 | 3.9984 | 7 | 5% | 0% | 0% | 0% | 0% | 35% | 15% | 0% | 15% | 7% | 3% | 15% | 15% | 5% | 15% | 5% | 10% | 15% | 35% | 5% | 5% | 20% | 0% | 10% | 100% | 12.5% | 20.5% | 34.5% | 1.75% | 3.25% | 3.5% | 14% | 10% | 100%
Cross DB Migratio - Clustered | 791 | 1784 | 2766 | 3.4968 | 7 | 5% | 0% | 0% | 0% | 0% | 35% | 15% | 0% | 15% | 7% | 3% | 15% | 15% | 5% | 15% | 5% | 10% | 15% | 35% | 5% | 5% | 20% | 0% | 10% | 100% | 12.5% | 20.5% | 34.5% | 1.75% | 3.25% | 3.5% | 14% | 10% | 100%
Refactor Java - Java/MW upgrade | 200 | 291 | 357 | 1.785 | 6 | 0% | 10% | 15% | 0% | 30% | 5% | 0% | 5% | 5% | 10% | 5% | 10% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
Refactor Java - Spring, Hibernate | 637 | 1407 | 2177 | 3.4176 | 6 | 0% | 10% | 10% | 0% | 30% | 5% | 0% | 5% | 10% | 10% | 5% | 10% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
Refactor Java - Middleware Migration | 239 | 349 | 428 | 1.7908 | 6 | 0% | 10% | 0% | 0% | 40% | 5% | 0% | 5% | 10% | 10% | 5% | 10% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
Refactor Java - UI Modernization |  |  |  |  | 6 | 0% | 20% | 15% | 0% | 25% | 5% | 0% | 5% | 5% | 7% | 3% | 10% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
Refactor Java - Stateless & scalable |  |  |  |  | 6 | 0% | 10% | 15% | 0% | 30% | 5% | 0% | 5% | 5% | 10% | 5% | 10% | 15% | 5% | 15% | 5% | 10% | 15% | 45% | 5% | 5% | 10% | 0% | 10% | 100% | 12.5% | 21.5% | 40.5% | 1.75% | 3.25% | 3.5% | 7% | 10% | 100%
[5 empty] | These tracks need to be validated with real implementations | [20 empty] | 25% | PM
[26 empty] | 25% | Architect
[26 empty] | 15% | Test Lead
[26 empty] | 20% | Sr.Developer
[26 empty] | 15% | Sr. Testers

## Lookup (hidden)
Complexity Scale Factors |  | OS Complexity Lookup |  | Business Rule /UI Complexity/Workflows |  | Source to Target Framework |  | Source to Target Database |  | App Size Complexity Look up |  |  |  | DB Size Lookup |  | Data Size Loopkup |  | Architecture Lookup |  | Third Party Components |  | Environment Lookup |  | External Interfaces |  | Internal Interfaces |  | Concurrent Usage |  | Location Complexity |  | I18N and L10N Complexity |  | Document availability
|  | 6 |  | 2 |  | 6 |  | 4 |  | 6 |  |  |  | 6 |  | 4 |  | 3 |  | 4 |  | 2 |  | 2 |  | 2 |  | 3 |  | 2 |  | 3 |  | 4
|  | Source Target OS | Complexity Rating | Criteria | Complexity Rating/Workflows | Source to Target Framework | Complexity Rating | Source to Target Database | Complexity Rating | Source code Size | Complexity Rating | No. of App objects (Screens, Reports, Programs) | Complexity Rating | No. of DB Objects | Complexity Rating | Data suze (MB) | Complexity Rating | Architecture | Complexity Rating | No. of 3rd Party Components | Complexity Rating | No. of Env | Complexity Rating | No. of Ext Interfaces | Complexity Rating | No. of internal Interfaces | Complexity Rating | Concurrent Users | Complexity Rating | Location | Complexity Rating | I18N/L10N Requirements | Complexity Rating | Test case availability | Complexity Rating
|  | Win 2016 to Win 2016 | 0 | Simple | 0 | .Net 4.5 to .Net 4.6 | 0 | Oracle 5 to 12c | 7 | 0-14k | 0 | <25 | 0 | 0-30 tables | 0 | Upto 100 GB | 0 | Unclustered | 0 | None | 0 | Upto 1 | 0 | Upto2 | 0 | Upto2 | 0 | Upto 50 | 0 | Single location | 0 | None | 0 | 90-100% | -2
|  | Win 2012 to Win 2016 | 0 | Medium | 1 | .Net 4.0 to .Net 4.6 | 1 | Oracle 6 to 12c | 6 | 15-49k | 1 | 25-49 | 1 | 31-60 tables | 1 | 100-300 GB | 2 | Clustered 3 tier | 3 | upto 5 | 1 | 2 to 3 | 1 | 2-5 | 1 | 2-5 | 1 | 50 to 100 | 1 | Multi-location | 1 | Only UI | 1 | 70-90% | -1
|  | Win 2008 Win 2016 | 2 | Complex | 2 | .Net 3.5 to .Net 4.6 | 2 | Oracle 7 to 12c | 5 | 50-99k | 2 | 50-74 | 2 | 61-90 tables | 2 | 300-500GB | 4 | Large Enterprise H/A | 6 | 6 to 10 | 2 | 4 to 5 | 2 | 6-10 | 2 | 6-10 | 2 | 100-200 | 2 | Multi-location,Language | 2 | UI+Data - single byte | 2 | 70% available | 0
|  | Win 2008 to Win 2012 | 2 | Not Avl | 1 | .Net 3.0 to .Net 4.6 | 4 | Oracle 8 to 12c | 4 | 100 - 199k | 3 | 75-89 | 3 | 91-120 tables | 3 | 500 - 750GB | 5 | Not Avl | 0 | 11 to 15 | 3 | 6 to 7 | 3 | 11-15 | 3 | 11-15 | 3 | 200-500 | 3 | Not Avl | 0 | UI+Data-Multi-byte | 3 | 60-70% | 1
|  | Win 2003 to Win 2016 | 6 | NA | 0 | .Net 2.0 to .Net 4.6 | 6 | Oracle 9 to 12c | 3 | 200-299k | 4 | 90-109 | 4 | 121-150 tables | 4 | 750GB-1TB | 6 | NA | 0 | 16 to 20 | 4 | 7 to 8 | 4 | 16-20 | 4 | 16-20 | 4 | 500-1000 | 4 | NA | 0 | Not Avl | 0 | 40-60% | 2
|  | Win 2003 to Win 2012 | 6 |  |  | Not Avl | 2 | Oracle 10g to 12c | 2 | 300-399k | 5 | 110-129 | 5 | 151-180 tables | 5 | 1TB - 1.5TB | 8 |  |  | 21 to 25 | 5 | Not Avl | 1 | 21-25 | 5 | 21-25 | 5 | 1000-1500 | 5 |  |  | NA | 0 | 20-40% | 3
|  | Win 2000 to Win 2012 | 8 |  |  | NA | 0 | Oracle 11g to 12c | 1 | 400-499k | 6 | 130-149 | 6 | 181-210 tables | 6 | 1.5TB-2TB | 10 |  |  | 26-30 | 6 | NA | 0 | 26 to 30 | 6 | 26-30 | 6 | 1500-2000 | 6 |  |  |  |  | 0-20% | 4
|  | Win 2000 to Win 2016 | 8 |  |  | Java EE7 to JavaEE7 | 0 | Oracle 12c to 12c | 0 | 500-599K | 7 | 150-169 | 7 | 211-240 tables | 7 | Not Avl | 2 |  |  | Not Avl | 2 |  |  | 31 to 35 | 7 | 31 to 35 | 7 | 2000-2500 | 7 |  |  |  |  | Not Avl | 0
|  | Win NT 4 Win 2016 | 10 |  |  | Java EE6 to Java EE7 | 1 | SQL Server 2000 to 2016 | 7 | 600-699K | 8 | 170-189 | 8 | 241-270 tables | 8 | NA | 0 |  |  | NA | 0 |  |  | Not Avl | 1 | Not Avl | 1 | Not Avl | 0 |  |  |  |  | NA | 0
|  | Win NT 4 to Win 2012 | 10 |  |  | Java EE5 to JavaEE7 | 2 | SQL Server 2005 to 2016 | 6 | 700-799K | 9 | 190-220 | 9 | 271-300 tables | 9 | [8 empty] | NA | 0 | NA | 0 | NA | 0
|  | RH7 to RH7 | 0 |  |  | J2EE 1.4 to JavaEE7 | 4 | SQL Server 2008 to 2016 | 4 | Not Avl | 2 | Not Avl | 2 | Not Avl | 3 | Lotus Notes Data
|  | Suse11 to Suse 11 | 0 |  |  | J2EE1.3 to Java EE7 | 6 | SQL Server 2012 to 2016 | 2 | NA | 0 | NA | 0 | NA | 0 | Upto 5GB | 0
Effort from 3 Point Estimator Model |  | RH6 to RH7 | 2 |  |  | J2EE1.2 to JavaEE7 | 8 | SQL Server 2014 to 2016 | 1 |  |  | Lotus Notes |  |  |  | 5GB to 10GB | 2
Simple Effort | 200 | Suse 10 to Suse 11 | 2 |  |  | Not Avl | 2 | SQL Server 2016 to 2016 | 0 |  |  | Upto 15 | 0 |  |  | 10GB to 15GB | 4
Medium Effort | 200 | RH5 to RH 7 | 4 |  |  | NA | 0 | MySQL v 3.xMySQL v 5.7 | 7 |  |  | 16-25 | 3 |  |  | 15GB to 30GB | 6
Complex Effort | 250 | Suse 9 to Suse 11 | 4 |  |  | Access 2013 to .Net | 0 | MySQL v 4.xMySQL v 5.7 | 6 |  |  | 26-40 | 6 |  |  | 30GB to 50GB | 8
Complex/Simple Ratio | 1.25 | RH4 to RH7 | 6 |  |  | Access 2010 to .Net | 1 | MySQL v 5.0MySQL v 5.7 | 4 |  |  | 41-60 | 8 |  |  | 50GB to 70GB | 10
|  | Suse 8 to Suse 11 | 6 |  |  | Access 2007 to .Net | 2 | MySQL v 5.1MySQL v 5.7 | 3 |  |  | 61-80 | 10 |  |  | 70GB to 100GB | 12
Source to TargetOS |  | RH3 to RH7 | 8 |  |  | Access 2003 to .Net | 4 | MySQL v 5.5MySQL v 5.7 | 2 |  |  | 81-100 | 12 |  |  | Not Avl | 2
Business Rule/UIComplexity |  | AIX 7.2 to Linux | 2 |  |  | Access 2002 to .Net | 6 | MySQL v 5.6MySQL v 5.7 | 1 |  |  | Not Avl | 3 |  |  | NA | 0
Source to Target Framework |  | Solaris 11.x to Linux | 2 |  |  | Access 2000 to .Net | 8 | MySQL v 5.7MySQL v 5.7 | 0 |  |  | NA | 0
Soure to Target Middleware |  | HP UX 11i V3 to Linux | 2 |  |  | NA | 0 | Not Available | 4
Source to target DB |  | AIX 7.1 to Linux | 4 |  |  | Not Avl | 3 | NA | 0
App Size Complexity (SLOC, Screens, reports) |  | Solaris 10 to Linux | 4 |  |  |  |  | Relational to Relational w/o StoredProc | 2
DB Size/No. of DB Objects |  | AIX 6.1 to Linux | 6 |  |  |  |  | Relational to Relational with StoredProc | 4
Data Size |  | HP UX 11i V2 to Linux | 6 |  |  |  |  | Mainframe DB2 to Relational | 6
No. of 3rd Party Components |  | Solaris 9 to Linux | 6 |  |  |  |  | Mainframe DB2 and VSAM to relational | 8
No. of Environments |  | AIX 5L5.1,5.2, 5.3 to LINUX | 8 |  |  |  |  | DB 400 to Relational | 8
No. of Ext Interfaces |  | Solaris 8,7 to Linux | 8 |  |  |  |  | Mainframe IMS to Relational | 10
No. of internal Interfaces |  | HP UX 11i V1 to Linux | 8 |  |  |  |  | Not Avl | 2
Architecture Complexity |  | Not Avl or Medium Complexity | 4 |  |  |  |  | NA | 0
Concurrent users
Location |  | NA | 0
Internationalization/Localization
Doc /Data Availability
Workflow |  | Source to TargetOS | Business Rule/UIComplexity | [6 empty] | Soure to Target Middleware | Source to target DB | DB Size/No. of DB Objects | Data Size | No. of Environments | No. of Ext Interfaces |  |  | Architecture Complexity | Concurrent users | Internationalization/Localization | Doc /Data Availability